Government of Lao PDR, Ministry of Agriculture and Forestry

Lao Landscapes and Livelihoods Project                       (P 170559)

Draft

ENVIRONMENTAL and SOCIAL

COMMITMENT PLAN (ESCP)

July 15th, 2020

Version 3

ENVIRONMENTAL AND SOCIAL COMMITMENT PLAN

- The Government of Lao PDR through the Ministry of Agriculture and Forestry will implement the Lao Landscapes and Livelihoods Project (the Project), with the key responsibly agency being the Department of Forestry but also others such as the Department of Planning and Finance, and collaborating agencies such as the Ministry of Natural Resources and Environment and the Ministry of Information, Culture and Tourism and others. The World Bank (hereinafter the Bank) has agreed to provide financing for the Project.

- The Government of Lao PDR through the Ministry of Agriculture and Forestry will implement material measures and actions so that the Project is implemented in accordance with the Environmental and Social Standards (ESSs). This Environmental and Social Commitment Plan (ESCP) sets out material measures and actions, any specific documents or plans, as well as the timing for each of these.

- The Government of Lao PDR through the Ministry of Agriculture and Forestry will also comply with the provisions of any other E & S documents required under the ESF and referred to in this ESCP, such as Environmental and Social Management Plans (ESMP), Resettlement Action Plans (RAP), Indigenous Peoples Plans (IPPs), and Stakeholder Engagement Plans (SEP), and the timelines specified in those E & S documents.

- The Government of Lao PDR through the Ministry of Agriculture and Forestry is responsible for compliance with all requirements of the ESCP even when implementation of specific measures and actions is conducted by the Ministry, agency or unit referenced in 1. above.

- Implementation of the material measures and actions set out in this ESCP will be monitored and reported to the Bank by the Government of Lao PDR through the Ministry of Agriculture and Forestry as required by the ESCP and the conditions of the legal agreement, and the Bank will monitor and assess progress and completion of the material measures and actions throughout implementation of the Project.

- As agreed by the Bank and the Government of Lao PDR through the Ministry of Agriculture and Forestry, this ESCP may be revised from time to time during Project implementation, to reflect adaptive management of Project changes and unforeseen circumstances or in response to assessment of Project performance conducted under the ESCP itself. In such circumstances, the Government of Lao PDR through the Ministry of Agriculture and Forestry will agree to the changes with the Bank and will update the ESCP to reflect such changes. Agreement on changes to the ESCP will be documented through the exchange of letters signed between the Bank and the Government of Lao PDR through the Ministry of Agriculture and Forestry. The Government of Lao PDR through the Ministry of Agriculture and Forestry will promptly disclose the updated ESCP.

- Where Project changes, unforeseen circumstances, or Project performance result in changes to the risks and impacts during Project implementation, the Government of Lao PDR through the Ministry of Agriculture and Forestry shall provide additional funds, if needed, to implement actions and measures to address such risks and impacts, which may include environmental (e.g. deforestation, reduced wildlife, water/ air pollution, soil erosion, littering), health (e.g. injuries due to UXO), and safety impacts (e.g. accident during field patrols and physical activities by participation of villagers ), gender-based violence (e.g. children labor force for under aged 15, sexual abuse) or impacts on indigenous peoples (e.g. exclusion, inequality of involvement and benefit sharing).

| MATERIAL MEASURES AND ACTIONS | TIMEFRAME | RESPONSIBILE ENTITY/AUTHORITY |
| --- | --- | --- |
| MONITORING AND REPORTING |
| A | REGULAR REPORTING Prepare and submit to the Bank regular monitoring reports on the environmental, social, health and safety (ESHS) performance of the Project, including but not limited to the implementation of the ESCP, status of preparation and implementation of E&S documents required under the ESCP, stakeholder engagement activities, and functioning of the Grievance Redress Mechanism (GRM). | Biannual reports (year 1-4), annual reports (year 5-7) | DoF/ MAF |
| B | INCIDENTS AND ACCIDENTS Promptly notify the Bank of any incident or accident related to the Project which has, or is likely to have, a significant adverse effect on the environment, the affected communities, the public or workers. Incidents and accidents with significant adverse effects include car/ traffic accidents, accidents during construction of buildings and field operations. They also include criminal acts against persons related to the Project such as staff and beneficiaries, as well as violence against children and women. Provide sufficient detail regarding the incident or accident, indicating immediate measures taken or that are planned to be taken to address it, and any information provided by any contractor and supervising entity, as appropriate. Subsequently, as per the Bank’s request, prepare a report on the incident or accident and propose any measures to prevent its recurrence. | Notify the Bank immediately by email, at least within 2 workdays after taking notice of the incident or accident. A report with sufficient detail on the incident or accident will be submitted to the Bank within 10 workdays. | DoF/ MAF |
| C | CONTRACTORS MONTHLY REPORTS Progress of construction/ refurbishment including summaries of contractor’s monthly monitoring reports are provided within the context of the regular reporting (item A). Upon request by the Bank, contractor’s monthly reports will be submitted. | Biannually (year 1-4), annually (year 5-7) | DoF/ MAF |
| ESS 1: ASSESSMENT AND MANAGEMENT OF ENVIRONMENTAL AND SOCIAL RISKS AND IMPACTS |
| 1.1 | ORGANIZATIONAL STRUCTURE Establish and maintain an organizational structure with qualified staff and resources to support management of E&S impacts and risks. This includes to appoint E&S focal points (each 1 for environment and social) within the Project Management Units to be responsible for the daily management and supervision of environmental and social risks and impacts at central level in DoF/ MAF, as well as in each participating provinces in PAFO and districts in DAFO. Additionally and according to needs, E&S specialists will be appointed within DoF/ MAF (DoE, DCC/ MoNRE), LFNC, LWU and MoH such as related to biodiversity, health and safety, pollution, violence against children/ women and others. Related documents will be submitted to the Bank. Procure and deploy two national consultants with expertise in environmental and social safeguards to provide intermittent inputs and support to the E&S focal points and specialists, including training, supervision and reporting. | Appoint E&S focal points prior to the Project effectiveness, latest by February 2021. They should be maintained and available throughout the Project implementation. Throughout the Project implementation, available for agreed periods. Procure/ deploy 2 national consultants within 3 months after Project effectiveness, latest by June 2021. | DoF/ MAF DoF/ MAF, DoE/ DCC MoNRE, Lao Front for National Construction (LFNC), Lao Women Union (LWU), Ministry of Health (MoH) DoF/ MAF |
| 1.2 | ENVIRONMENTAL AND SOCIAL ASSESSMENT Apply and update Environmental and Social Impact and Risk Assessments for all sub-projects prepared and proposed during the implementation of the Project. The assessments will include identified sub-project specific environmental and social impacts and risks, as well as proposed measures to avoid and mitigate them. This will be done in accordance to the processes and tools as of the agreed ESMF and in a manner acceptable to the Bank. | Apply Environmental and Social Impact and Risk Assessments for all proposed subprojects throughout the Project. Update Environmental and Social Impact Assessment process after experiences gained latest by August 2022 (year 2). | DoF/ MAF, DoE/ MoNRE |
| 1.3 | MANAGEMENT TOOLS AND INSTRUMENTS Apply and update the prepared Environmental and Social Management Framework (ESMF) for the Project, which informs sub-project design and implementation and include: Environmental and social screening/ assessment (ESA), environmental and social management plan (ESMP), Strategic Environmental and Social Assessment (SESA), Pest Management Plan (PMP), Environmental Code of Practice (ECoP), UXO Safety and Clearance Protocol, List of Do’s and Dont’s (wildlife trade and solid waste), Labor Management Procedures (LMP), Community Health and Safety Plan (CHSP), Gender-based Violence (GBV) and Violence against Children (VAC) and Cultural Heritage Framework. Apply and updated the Projects Stakeholder Engagement Plan (SEP) and Community Engagement Framework (CEF). The SEP includes stakeholder analysis and Grievance Redress Mechanism (GRM). The CEF includes the Ethic Group Development Framework (EGDF), the Access Restriction Framework (ARF) and the Resettlement Policy Framework (RPF). Incorporate results of applying ESMF, SEP and CEF into subproject proposals and submit the Bank for approval (for subprojects > x US$). | Apply tools and instruments related to ESMF, SEP and CEF throughout the Project implementation. Update tools and instruments related to ESMF, SEP and CEF after experiences gained, latest by August 2022 (year 2). Throughout the Project implementation, prior to subproject implementation/ bidding from September 2021 onwards. | DoF, DoFI, Department of Agriculture (DoA)/ MAF, DoE/ MoNRE, Ministry of Labor and Social Welfare (MoLSW), LAO Women Union (LWU), Lao Front for National Construction (LFNC), Ministry of Information, Culture and Tourism (MoICT) |
| 1.4 | MANAGEMENT OF CONTRACTORS Incorporate the relevant aspects of the ESMF, such as the Environmental Code of Practice (ECoP), the List of Do’s and Dont’s on wildlife trade and solid waste and the Labor Management Procedures (LMP) into the ESHS specifications of the procurement documents with contractors. Ensure that the contractors comply with the ESHS specifications of their respective contracts. Monitoring of this compliance will be conducted by E&S focal points at all levels, supported by specialists or hired/ external supervision in case it is required. | Prior to the start of bidding during preparation of the procurement documents from September 2021 onwards. Monitor and supervise the compliance with the ESHS throughout Project implementation from January 2022 onwards. | DoF/ MAF |
| ESS 2: LABOR AND WORKING CONDITIONS |
| 2.1 | LABOR MANAGEMENT PROCEDURES Apply and update the Labor Management Procedures (LMP) that have been developed for the Project as part of the ESMF. The LMP will apply to project personnel and contractors hired under the Project. The LMP will ensure that safe accommodation and transport, first aid-kits and emergency procedures are available at working sites, and that Social Security (health and life insurance) is provided according to the Labour Law. | Monitor and supervise the compliance throughout Project implementation from January 2022 onwards. | DoF/ MAF |
| 2.2 | GRIEVANCE MECHANISM FOR PROJECT WORKERS Establish and implement a dedicated grievance mechanism as part of the Labour Management Procedures (LMP) for Project workers, as part of the ESMF and consistent with ESS2. | The grievance mechanism will be operational prior to engaging Project workers latest by December 2021 and maintained throughout the Project implementation. | DoF/ MAF |
| 2.3 | OCCUPATIONAL HEALTH AND SAFETY (OHS) MEASURES Apply occupational, health and safety (OHS) measures as specified in the Labour Management Procedures (LMP) and the subproject specific Environmental and Social Management Plan (ESMP). | OHS measures applied and monitored from January 2022 onwards throughout the Project implementation. | DoF/ MAF |
| ESS 3: RESOURCE EFFICIENCY AND POLLUTION PREVENTION AND MANAGEMENT [the relevance of ESS3 is established during the ESA process. ESS3 may require the adoption of specific measures to cover energy, water and raw materials use, management of air pollution, hazardous and nonhazardous wastes, chemicals and hazardous materials and pesticides. Depending on the project, these measures may be set out in an E&S document (e.g. ESMP) already mentioned in the section under ESS1 above or as a stand-alone document or a separate action. Indicate whether ESS3-related measures are covered under an existing document or as stand-alone actions. See examples below]. |
| 3.1 | E-WASTE MANAGEMENT PLAN: In case it is relevant, E-Waste management will be specified in subproject related ESMP. | Applied and monitored for relevant subprojects, from January 2022 onwards throughout the Project implementation. | DoF/ MAF |
| 3.2 | RESOURCE EFFICIENCY AND POLLUTION PREVENTION AND MANAGEMENT: Apply resource efficiency and pollution prevention and management measures as specified in the Environmental Code of Practice (ECoP), Pest Management Plans (PMP) and List of Do’s and Don’ts as part of the ESMF. Specific resource efficiency and pollution prevention and management measures to effectively manage wastes and hazardous materials will be developed and implemented in the context of subproject specific ESMPs. | Apply and monitor for relevant subprojects, from January 2022 onwards throughout the Project implementation. | DoF/ MAF |

| ESS 4: COMMUNITY HEALTH AND SAFETY [the relevance of ESS4 is established during the ESA process. As with ESS3, ESS4 may require the adoption of specific measures that may be set out in an E&S document (e.g. ESMP) already mentioned in the section under ESS1 above or as a stand-alone document or a separate action. Indicate whether ESS4-related measures are covered under an existing document or as stand-alone actions. See examples below]. |
| --- |
| 4.1 | TRAFFIC AND ROAD SAFETY: Deploy and apply traffic and road safety risk management measures as specified in subproject specific ESMPs, guided by Labor Management Procedures (LMP) of the EMSF. | Deploy by September 2021, apply and monitor after throughout the Project implementation. | DoF/ MAF |
| 4.2 | COMMUNITY HEALTH AND SAFETY: Apply measures and action to assess and manage specific risks and impacts to the community arising from Project activities, such as behavior of Project workers, risks of labor influx, response to emergency situations as specified in Community Health and Safety Plans (CHSP) as part of subproject specific ESMPs. The ESMF includes procedures for screening planned subproject activities for community health and safety risks, and includes screening of proposed construction works for community health and safety risks on a case by case basis prior to implementation. | Apply and monitor from January 2022 onwards throughout the Project implementation in the context of sub-project preparation and implementation. | DoF/ MAF |
| 4.3 | GBV AND SEA RISKS: Apply Gender-Based Violence and Sexual Exploitation and Abuse risk management measures designed to manage the risks of project activities exacerbating gender-based violence, including violence against children, sexual abuse and risk of exclusion of disadvantaged groups (on the basis of gender or ethnicity). Related measures are incorporated into subproject specific ESMPs, guided by the related guideline of the ESMF. | Apply and monitor from September 2021 onwards throughout the Project implementation in the context of sub-project preparation and implementation. | DoF/ MAF |
| 4.4 | GBV AND SEA RISKS DURING PROJECT IMPLEMENTATION: Engage an experienced female national counselor to facilitate safe disclosure and referral of issues that may be received through the project Grievance Redress Mechanism (GRM) counselling hotline. | To be in place 1 month after Project effectiveness, latest by April 2021. | DoF/ MAF |
| 4.4 | SECURITY PERSONNEL: Relevant only for major construction sites, to ensure work site security to be financed, applied and monitored by engaged construction companies. Qualification of Contractor based on bidding criteria, personal protection equipment and others as required. | From January 2022 onwards and throughout the Project implementation. | DoF/ MAF, contractors |

| ESS 5: LAND ACQUISITION, RESTRICTIONS ON LAND USE AND INVOLUNTARY RESETTLEMENT [the relevance of ESS5 is established during the ESA process. If during Project preparation, it is determined that resettlement documents need to be prepared, this should be reflected in the ESCP. See examples below] |
| --- |
| 5.1 | RESETTLEMENT PLANS: Prepare and implement Resettlement Plans (RAPs) in accordance with ESS 5, consistent with the requirements of the Resettlement Policy Framework (RPF) of the ESMF and acceptable to the Bank. RAPs will be prepared, implemented and monitored in the context of subproject preparation and implementation, only if relevant (land acquisition, restrictions on land use). The RAPs need to be submitted to and approved by the Bank prior to implementing concerned subprojects. | RAPs to be submitted together with subproject proposals to the Bank prior to their implementation from September 2021 onwards throughout the Project implementation. | DoF/ MAF |
| 5.2 | GRIEVANCE MECHANISM Establish and implement a Grievance Redress Mechanism (GRM) in accordance to the requirements of the Stakeholder Engagement Plan (SEP) of the ESMF to address and resolve complaints in accordance to ESS5. | Establish the GRM prior to implement subprojects and resettlements until January 2022 and maintain it after throughout the Project implementation. | DoF/ MAF |
| ESS 6: BIODIVERSITY CONSERVATION AND SUSTAINABLE MANAGEMENT OF LIVING NATURAL RESOURCES [the relevance of ESS6 is established during the ESA process. As with other ESSs, ESS6 may require the adoption of specific measures that may be set out in an E&S document (e.g. ESMP) already mentioned in the section under ESS1 above or as a stand-alone document or a separate action. Indicate whether ESS6-related measures are covered under an existing document or as stand-alone actions. See examples below]. |
| 6.1 | BIODIVERSITY RISKS AND IMPACTS: Formulate, apply and monitor measures to avoid and minimize impacts and risks of proposed subprojects towards biodiversity within the Projects landscapes in accordance with the ESMF, especially based on Environmental and Social Screening/ Assessment (ESA), and incorporated into Environmental and Social Management Plans (ESMP), Pest Management Plans (PMP) and guided by List of do’s and Don’t’s on wildlife trade and consumption. Screening/ assessment of potential adverse impacts and risks towards biodiversity is done in the context of subproject proposal preparation, and based on relate results appropriate measures are included into the ESMPs in accordance with specifications of the ESMF, and in a manner acceptable to the Bank. | Apply from September 2021 onwards for sub-project proposal preparation prior to implement subprojects throughout the Project implementation. | DoF/ MAF |
| ESS 7: INDIGENOUS PEOPLES/SUB-SAHARAN AFRICAN HISTORICALLY UNDERSERVED TRADITIONAL LOCAL COMMUNITIES [See examples of possible actions below, if determined that ESS7 is relevant]. |
| 7.1 | INDIGENOUS PEOPLES PLAN: Prepare, implement and monitor measures to benefit ethnic groups in the context of preparing and implementing relevant subprojects in accordance to the requirements of the Ethnic Group Development Framework (EGDF) of the ESMF, the ESS7, and in a manner acceptable to the Bank. | Prior to the implementation of subprojects by January 2022 and throughout the Project implementation. | DoF/ MAF |
| 7.2 | GRIEVANCE MECHANISM: Establish and implement arrangements for the grievance mechanism for indigenous people, as required under the IPPF and further described in the Grievance Redress Mechanism (GRM) in accordance to the requirements of the Stakeholder Engagement Plan (SEP) of the ESMF to address and resolve complaints in accordance to ESS7/10. | Prior to the implementation of subprojects by January 2022and throughout the Project implementation. | DoF/ MAF |
| ESS 8: CULTURAL HERITAGE [the relevance of ESS6 is established during the ESA process. As with other ESSs, ESS6 may require the adoption of specific measures that may be set out in an E&S document (e.g. ESMP) already mentioned in the section under ESS1 above or as a stand-alone document or a separate action. Indicate whether ESS8-related measures are covered under an existing document or as stand-alone actions. See examples below]. |
| 8.1 | CHANCE FINDS: It is assessed that minor civil works/ maintenance under the Project are unlikely to involve findings of artifacts of archaeological, cultural or historical importance. As the construction work and sites will only be determined in the course of the Project, basic procedures will be part of the ESA/ Screening and Cultural Heritage Framework (CHF) under the ESMF. | Apply screening and processes during subproject preparation by September 2021 and throughout the Project implementation. | DoF/ MAF |

| ESS 9: FINANCIAL INTERMEDIARIES [This standard is only relevant for Projects involving Financial Intermediaries (FIs). See below a couple of examples of actions that should be considered when FIs are involved.] |
| --- |
| 9.1 | ESMS: Not relevant. |  |  |
| 9.2 | FI ORGANIZATIONAL CAPACITY: Not relevant. |  |  |
| 9.3 | SENIOR MANAGEMENT REPRESENTATIVE: Not relevant. |  |  |
| ESS 10: STAKEHOLDER ENGAGEMENT AND INFORMATION DISCLOSURE |
| 10.1 | STAKEHOLDER ENGAGEMENT PLAN PREPARATION AND IMPLEMENTATION Implement and update the Stakeholder Engagement Plan (SEP) to ensure that all relevant stakeholders are appropriately engaged and consulted. | Implement the SEP throughout the Project implementation. Update the SEP after experiences gained latest by August 2022 (year 2). | DoF/ MAF |
| 10.2 | PROJECT GRIEVANCE MECHANISM: Implement the Grievance Redress Mechanism (GRM) as part of the Stakeholder Engagement Plan (SEP) of the ESMF. The GRM includes provisions that cover requirements of ESS2, ESS5 (especially on land access restriction), ESS7 (indigenous peoples related aspects). | Implement the GRM from January 2022 onwards and throughout the Project implementation. | DoF/ MAF |
| CAPACITY SUPPORT (TRAINING) |
| CS1 | Training to be provided and targeted groups General training on the World Bank Environmental and Social Management Framework: Government officials involved in the Project (central level) Specific technical training on implementation of the Project’s ESMF: Project managers, E&S Focal Points, technical personnel (central, province, district level). Topics of these specific technical trainings include all aspects of the ESMF: Environmental and social screening/ assessment (ESA), Environmental and social management plan (ESMP), Strategic Environmental and Social Assessment (SESA), Pest Management Plan (PMP), Environmental Code of Practice (ECoP), UXO Safety and Clearance Protocol, List of Do’s and Dont’s (wildlife trade and solid waste), Labor Management Procedures (LMP), Community Health and Safety Plan (CHSP), Gender-based Violence (GBV) and Violence against Children (VAC) Cultural Heritage Framework, Stakeholder analysis and Grievance Redress Mechanism (GRM), Ethnic Group Development Framework (EGDF), Access Restriction Framework (ARF) Resettlement Policy Framework (RPF). | After the Project effectiveness latest by July 2021. After the Project effectiveness, especially in year 1 (2021) and 2 (2022). After only technical backstopping. All trainings to be completed prior to deployment of contractors to the field. | DoF/ MAF |