Government of Lao PDR, Ministry of Agriculture and Forestry

Laos Landscapes and Livelihoods Project (P 170559)

Stakeholders Engagement Plan (SEP)

Draft 3

July 28, 2020

TABLE OF CONTENTS

1.	Introduction	1

1.1	Principles for effective stakeholder engagement	2

1.2	Objective of Stakeholder Engagement Plan (SEP)	3

1.3	Project Description	4

2.	Brief Summary of Previous Stakeholder Engagement Activities	5

3.	Stakeholders Mapping (Identification and Analysis)	6

3.1 Project-affected Parties	6

3.2 Other Interested Parties	6

Development Partners	7

Local and National Non-governmental Organizations	8

3.3 Disadvantaged / Vulnerable Individuals or Groups	8

3.4 Stakeholders from Government Agencies	9

3.5 Summary of Project Stakeholders Needs	11

4.	Stakeholder Engagement Program	15

4.1 Purpose and Timing of Stakeholder Engagement Program	15

Engagement during Project Preparation	15

Engagement During Project Implementation	16

4.2 Proposed Strategy for Information Disclosure	19

4.3 Proposed Strategy for Consultation	24

4.4 Proposed Strategy to Incorporate the View of Vulnerable Groups	25

Free, Prior and Informed Consent FPIC	25

Engaging with Women	26

Engaging with Ethnic Groups	27

4.5 Timelines	28

4.6 Review of Comments	28

4.7 Future Phases of Project	29

5. Resources and Responsibilities for Implementing Stakeholder Engagement Activities	30

5.1 Resources	30

5.2 Management functions and responsibilities	30

6. Grievance Redress Mechanisms	31

6.1 Access to Justice and Grievance Redress Mechanism in Lao PDR	31

6.2 Key Fundamentals for GRM	34

6.3 Key Principles Guiding the Design of a Grievance Redress Mechanism	35

6.4 Details of Grievance Processing from Village to Central Level	36

Step 1: Village Level	36

Step 2: District Level	36

Step 3: Provincial Level	37

Step 4: Central Level	37

6.5 Steps Process to Redress Grievances	38

7. Monitoring and Reporting	39

7.1 Involvement of Stakeholders in Monitoring Activities	39

7.2 Reporting Back to Stakeholder Groups	39

Annex	41

Annex 1: Technical Note: Public Consultations and Stakeholder Engagement in WB-supported operations when there are constraints on conducting public meetings March 20, 2020	41

Annex 2: Lao PDR Legal Instruments Related to Grievance Redress	45

Annex 3   Details of the 7 steps of the LLL Grievance Resolution	48

Annex 4: Provisional budget for the SEP	55

Table ot tables

Table 1: Summary of past consultations	5

Table 2: Landscape and economic drivers	6

Table 3: Interested partie’ stake and interest in the project	7

Table 4: Institutions and project implementation role	9

Table 5: Summary of Project Stakeholders Needs	11

Table 6: Engagement during project preparation	15

Table 7: Engagement During Project Implementation	15

Table 8: Proposed Strategy for Information Disclosure	19

Table 9: Means of communication	21

Table of figures

Figure 1	LLL Grievance Redress Mechanism	32

Figure 2: Steps process to redress grievances	37

ACRONYMS

| CLIPAD | Climate Protection through Avoided Deforestation |
| --- | --- |
| CSO | Civil Society Organizations |
| DAEC | Department of Agriculture Extension and Cooperative |
| DAFO | District Agriculture and Forest Office |
| DOF | Department of Forestry |
| DOFI | Department of Forest Inspection |
| ESF | Environment and Social Framework |
| ESS | Environment and Social Standards |
| DOEA | Department of Ethic Afffairs |
| FPIC | Free Prior Inormed Consent |
| FSWG | Forest Sector Working Group |
| GIZ | Deutsche Gesellschaft für Internationale Zusammenarbeit |
| GGF | Green Growth Forum |
| LHD | Learning House for Development |
| LFNC LLL | Lao Front for Natioal Construction Laos Livelihoods and Landscapes Project |
| LWU | Lao Womens Union |
| IUCN | International Union for Conservation of Nature |
| INGO | International Non-Governnment Organizations |
| JICA | Japan International Cooperation Agency |
| KFW | Kreditanstalt für Wiederaufbau (Development Bank) |
| Lao WEN | Lao Wildlife Enforcement Network |
| LENS 2 | Second Lao Environmental and Social Project |
| LIWG | Land Issues Working Group |
| LNTA | Lao National Tourism Administration |
| MAF | Ministry of Agriculture and Forestry |
| M&E | Monitoring and Evaluation |
| MOHA | Ministry of Home AFfairs |
| MOICT | Ministry of Information, Culture and Tourism |
| MONRE | Ministry of Natural Resources and Environment |
| MPWT | Ministry of Public Work and Transportation |
| MPI | Ministry of Planning and Investment |
| NAFRI | National Agriculture and Forest Institute |
| NBCA | National Biodiversity Conservation Areas |
| NBSAP | National Biodiversity Strategy and Action Plan |
| NPA | National Protected Area |
| NPA | Non-Profit Associations |
| PA | Protected Area |
| PFA | Production Forest Area |
| PONRE | Provincial Office of Natural Resources and Environment |
| PRF | Poverty Reduction Fund |
| PSFM | Participatory Sustainable Forest Management |
| SCC | Swedish Chamber of Commerce |
| SEP | Stakeholders Engagement Plan |
| SUFORD | Sustainable Forestry for Rural Development |
| UNDRIP | Unigted States Declaration on the Rights of Indigenous Peoples |
| UNODC | United Nations Office on Drugs and Crime |
| VLD | Village Livelihood Development |
| WB | World Bank |
| WCS | Wold Conservation Society |
| WWF | World Wide Fund for Nature |

- Introduction

The World Bank’s Environmental and Social Framework (ESF) came into effect on October 1, 2018. The Framework includes Environmental and Social Standard (ESS) 10, “Stakeholder Engagement and Information Disclosure”, which recognizes “the importance of open and transparent engagement between the Borrower and project stakeholders as an essential element of good international practice”. ESS10 emphasizes that effective stakeholder engagement can significantly improve the environmental and social sustainability of projects, enhance project acceptance, and make a significant contribution to successful project design and implementation.

As defined by the 2018 ESF and ESS10, stakeholder engagement is an inclusive process conducted throughout the project life cycle. Where properly designed and implemented, it supports the development of strong, constructive and responsive relationships that are important for successful management of a project’s environmental and social risks. Key elements of ESS10 include:

“Stakeholder engagement is most effective when initiated at an early stage of the project development process, and is an integral part of early project decisions and the assessment, management and monitoring of the project.”

“Borrowers will engage with stakeholders throughout the project life cycle, commencing such engagement as early as possible in the project development process and in a timeframe that enables meaningful consultations with stakeholders on project design. The nature, scope and frequency of stakeholder engagement will be proportionate to the nature and scale of the project and its potential risks and impacts.

Borrowers will engage in meaningful consultations with all stakeholders. Borrowers will provide stakeholders with timely, relevant, understandable and accessible information, and consult with them in a culturally appropriate manner, which is free of manipulation, interference, coercion, discrimination and intimidation.

The process of stakeholder engagement will involve the following, as set out in further detail in this ESS: (i) stakeholder identification and analysis; (ii) planning how the engagement with stakeholders will take place; (iii) disclosure of information; (iv) consultation with stakeholders; (v) addressing and responding to grievances; and (vi) reporting to stakeholders.

The Borrower will maintain and disclose as part of the environmental and social assessment, a documented record of stakeholder engagement, including a description of the stakeholders consulted, a summary of the feedback received and a brief explanation of how the feedback was taken into account, or the reasons why it was not.”

Borrowers are required to develop a Stakeholder Engagement Plan (SEP) proportionate to the nature and scale of the project and its potential risks and impacts (paragraph 13). Stakeholders have to be identified and the SEP has to be disclosed for public review and comment as early as possible, before the project is appraised by the World Bank. ESS10 also requires the development and implementation of a grievance redress mechanism that allows project-affected parties and others to raise concerns and provide feedback related to the environmental and social performance of the project and to have those concerns addressed in a timely manner.

## Principles for effective stakeholder engagement

The project’s Stakeholder Engagement Plan (SEP) shall be informed by a set of principles defining its core values underpinning interactions with identified stakeholders. Common principles based on “International Best Practice” include the following:

- Commitment is demonstrated when the need to understand, engage and identify the community is recognised and acted upon early in the process;

Integrity occurs when engagement is conducted in a manner that fosters mutual respect and trust;

Respect is created when the rights, cultural beliefs, values and interests of stakeholders and affected communities are recognised;

Transparency is demonstrated when community concerns are responded to in a timely, open and effective manner;

Inclusiveness is achieved when broad participation is encouraged and supported by appropriate participation opportunities; and

Trust is achieved through open and meaningful dialogue that respects and upholds a

community’s beliefs, values and opinions.

Stakeholder engagement is the continuing and iterative process by which the Borrower identifies, communicates, and facilitates a two-way dialogue with the people affected by its decisions and activities, as well as others with an interest in the implementation and outcomes of its decisions and the project. It takes into account the different access and communication needs of various groups and individuals, especially those more disadvantaged or vulnerable, including consideration of both communication and physical accessibility challenges. Engagement begins as early as possible in project preparation because early identification of and consultation with affected and interested parties allows stakeholders’ views and concerns to be considered in the project design, implementation, and operation.

Meaningful stakeholder engagement throughout the project cycle is an essential aspect of good project management and provides opportunities for Borrowers to learn from the experience, knowledge, and concerns of the affected and interested stakeholders, and to manage their expectations by clarifying the extent of the Borrower’s responsibilities and resources.

Stakeholder engagement in the LLL Project planning and implementation, at all levels, is a question of both human rights and sustainability. In order to ensure transparency and accountability, stakeholder engagement needs to incorporate human rights and sustainability principles.

In the context of forest landscape in Protected Areas, stakeholder engagement is a means for tackling such issues as inappropriate land use and unsustainable natural resource management. Stakeholder engagement can thus be an important tool to implement nature conservation actions successfully and sustainably.

## Objective of Stakeholder Engagement Plan (SEP)

The overall objective of this Stakeholder Engagement Plan (SEP) is to define a program for stakeholder engagement, including public information disclosure and consultation, throughout the entire project cycle. The SEP outlines the ways in which LLL project will communicate with stakeholders and includes a mechanism by which people can raise concerns, provide feedback, or make complaints about LLL project and any activities related to the project.

The Key Objectives of the SEP as stated in the ESS-10 are to:

- To identify the roles and responsibility of all stakeholders and ensure their participation in the complete project cycle

Establish a systematic approach to stakeholder engagements that will help SPESSE identify stakeholders and build and maintain a constructive relationship with them, in particular project-affected parties

Assess the level of stakeholder interest and support for the project and to enable stakeholders’ views to be considered in project design and implementation

Promote and provide means for effective and inclusive engagement with project- affected parties throughout the project life -cycle on issues that could potentially affect them.

Ensure that appropriate project information on environmental and social risks and impacts is disclosed to stakeholders in a timely, understandable, accessible and appropriate manner and format with special consideration for the disadvantaged or vulnerable groups.

Provide project-affected parties with accessible and inclusive means to raise issues and grievances and allow EWSC to respond to and manage such grievances.

To devise a plan of action that clearly identifies the means and frequency of engagement of each stakeholder

To allocate budgetary and other resources in the project design, project implementation, and Monitoring and Evaluation (M&E) for stakeholder engagement and participation

This SEP is a living document and will be updated throughout the project lifecycle. It will be:

- Disclosed prior to project commencement;

Be the strategic tool for all project related engagements;

Periodically updated and changes validated during project implementation; and

Monitored and its effectiveness evaluated towards the end of the project

## Project Description

PDO is to improve sustainable forest management and enhance livelihoods opportunities in selected landscapes in Lao PDR. The Project have four components that together help convene and “crowd in” coordinated actions and investments in priority spatially explicit landscapes to achieve larger impact at scale than would be possible with small fragmented projects.

- Increase natural capital contribution to poverty reduction and greener economic growth, jobs, and livelihoods

- Better protection of globally unique ecosystems and biodiversity

- Improved resilience of villages and landscapes to flood, drought, erosion and other climate risks

- Greater private investment in tree plantations and nature-based tourism from companies committed to sustainability and helping protect natural assets.

- Contribution to Nationally Determined Contributions(NDC) GHG mitigation targets through maintained or restored forest cover

There are 4 main project components:

Component 1: Investing in Natural Wealth and Resilience in Forest Landscapes. The objective is to build natural capital in specific landscapes and investment sites throughout the forest estate.

Component 2: Livelihoods Opportunities for Forest Landscapes Sustainability. The objective is to improve natural resource-based livelihoods opportunities and vocational skills development among targeted villages within the forest landscapes supported under Component 1

Component 3: Institutions, Incentives and Information aims to enhance institutional capacities, policies, incentives, and information across sectors for sustainably deploying natural assets for greener economic growth from the forest estate

Component 4: Project Management, Monitoring and Learning

# Brief Summary of Previous Stakeholder Engagement Activities

There has been engagement with limited project stakeholders since the beginning of the preparation phase of the Environmental and Social Framework. Four main types of stakeholder engagement activities have taken place to date: informal communication with government agencies, virtual meeting, kick off meeting and first national workshop.

Table 1: Summary of past consultations

| Nb | Date | Venue | Objective | Sunmary of outcome | Participants |
| --- | --- | --- | --- | --- | --- |
| 1 | 18-22 May 2020 | Virtual Implementation Support Mission - Scaling-Up Participatory Sustainable Forest Management Project (SUFORD) | Introduction to the project and missio objectives | Present the LLL PAD, Update on progresses Present human resourcs PSFM model VLD model Present ESF | 13 WB team members, DOF, consultants |
| 2 | 12 June 2020 | Kick-off meeting ESF LLL project | Present workplan Clarify deliverable, templates, contents of documents | Workplan agreed upon by all participants including timeframe and milestone Modalities of consultation for prepapration phase | DOF 6, WB 6, Indufor 3 |
| 3 | End June | 1st National Workshop | SEP-ESCP | Record participants feedback and incorrporate releccant inuts in the SEP and ESCP | DOF, relevant government agencies, WB, mass organizations, representatives from province |

# Stakeholders Mapping (Identification and Analysis)

Stakeholders can be defined as groups that have a stake/interest/right in the forest and those that will be affected either negatively or positively by the LLL project activities. Stakeholder engagement involves (structured) processes meant to ensure participation on specific issues and broad, inclusive and continuous means to improve dialogue and decision-making at all stages of planning and implementation. The goal of the Stakeholders Engagement Plan is to achieve collective ownership of the process and to support conservation, sustainable forest management, and sustainable livelihood improvement schemes.

## 3.1 Project-affected Parties

The potentially (negatively) project-affected parties include the communities involved in project activities in the forest landscapes (to be refined according to the landscape selected,). However, based on experience gained from similar projects, such as SUFORD-SU, the project activities will not result in any major adverse environmental and social impacts that affect the livelihoods or the lives of the project-targeted beneficiaries; local communities in and around the project area including ethnic and / or vulnerable groups.

Table 2: Landscape and economic drivers

| Nb | Landscape | Economic drivers |
| --- | --- | --- |
| 1 | Khammouane landscape | Tourism around the “loop”, potential expansion of env and soc sustainable industrial tree plantations, 3rd party certified PFAs, VFM potential |
| 2 | Grearer Nam Et Phou Leuy | Tourism, VFM potential, and Carbon credits |
| 3 | Greater Phou Khao Khouay | Env and soc sustainable industrial tree plantations, tourism in and around PKK NPA, VFM potential |
| 4 | Savannakhet | Pulp mill (Xepon), potential for env and soc sustainable industrial tree plantations, VFM |
| 5 | Tor Sip & Phou Samsoum Provincial Protected Area | Tourism potential for proximity with VTE and Plain of Jars |

## 3.2 Other Interested Parties

Interested Parties include stakeholders who may not experience direct impacts from the Project but who consider or perceive their interests as being affected by the project and/or who could influence the project and the process of its implementation in some way. Specifically, this category will include the following individuals and groups.

Table 3: Interested partie’ stake and interest in the project

| Other interested parties | Interest in the project |
| --- | --- |
| Other project developpers/agencies | Can help Identify interactions and cumulative impacts with other proposed developments |
| Private sector | Support plantation and ecotourism in significant areas |
| Tourism sector | Promote sustianable ecotourism |
| Non Government Organizations/Civil Society Organizations | Ensure the environmental and social performance of the Project is protecting the environment and affected people and complies with international E&S standards |
| General public | Interest in the general socio-economic impacts of the project, both adverse and beneficial |
| Press and media | Inform residents in the project area and the wider public about the Project implementation and planned activities |

### Development Partners

Development partners will be employed in roles that suit their specific strengths and capabilities. For example, partnership with national and regional universities will be explored to assist with identification of possible livelihood options, and to carry out feasibility studies, including market studies, of identified livelihood options.

Forest Sector Working Group, Green Growth Forum, missions for SUFORD and LENS 2 IPFs, REDD+ readiness and ERPA, and others. Informal and bilateral consultations were also held with GIZ and KFW (on biodiversity conservation, PA management, village forestry and REDD+), AFD (SFM, livelihoods, green growth), ADB (biodiversity conservation, FIP), IFC (FIP and sustainable agroforestry), JICA (MRV and emissions reduction monitoring), GEF (Biodiversity and Land Degradation), UNODC (IWT and forest law enforcement), ACIAR (action research agenda and legal support to policy development), WCS (technical support to PA management).

### Local and National Non-governmental Organizations

Local NGOs and initiative/advocacy groups particularly those focusing on social development issues represent the considerable capacity that the project(s) may tap for disseminating information and raising awareness of the planned activities among the potentially affected communities in the project area.

Several NGOs and other development partners are active in NPAs, most notably the Wildlife Conservation Society (WCS), World Wide Fund for Nature, and Lao Wildlife Conservation Association (LWCA), and there would be merit in building on some of this activity to add value to and avoid duplication and/or dilution of effort. Land Issues Working Group

In terms of local NPA, the Lao NPA Network / Learning House for Development (LHD) s an informal network of Non-Profit Associations (NPAs) involved in development work in the Lao PDR with the main purpose of enhancing mutual coordination, cooperation and solidarity, sharing information and assistance between network members and for joint capacity building of its members.

## 3.3 Disadvantaged / Vulnerable Individuals or Groups

Disadvantaged / vulnerable individuals or groups are potentially disproportionally affected and less able to benefit from opportunities offered by the project due to specific difficulties to access and/or understand information about the project and its environmental and social impacts and mitigation strategies. It includes poor households, ethnic minorities, women, disabled, and youth.

While the project envisages to transform different communities and create a lasting impact in the forest landscapes, the probability of certain groups of people feeling discontent is possible. These people could be beneficiaries or non-beneficiaries of the project. Other groups are susceptible to exclusion from, and/or are unable to fully participate in the mainstream consultation processes and as such may require specific measures and assistance to ensure adequate inclusion in project activities. Women and children, elderly, disabled and chronically ill are oftentimes the most vulnerable because of their limited access to information due to physical, social, cultural and structural barriers within the communities. These categories of people will be given particular attention through targeted methods that will enable information sharing and understanding of the nature of project activities and the anticipated positive and potential negative impacts of the project as well as their expectations. Specific meetings and focus groups as well as individual household visits with these groups of people with specific and tailored messages will be used in consideration of their existing challenges.

Another envisaged challenge is low literacy levels in some of the targeted communities that will make it difficult for beneficiaries to read and understand written information related to the project. This challenge is even more exacerbated if the documents are in English. These groups of people will be engaged through interpersonal communication approaches such as meetings, demonstrations, focus group discussions, use of images and illustrations.

The non-beneficiary members of the target communities will also be engaged to ensure that they understand the project targeting processes and capacity and resource limits so that they don’t feel neglected. This situation may likely be experienced in the disbursement of the village livelihood grants.

In many communities, women and girls, despite bearing a huge burden of care and responsibilities, their participation especially where grants and compensations are being made, is very minimal. Therefore, to ensure equal participation of men and women at every level of project implementation, deliberate efforts will be made according to the current government policies aiming to improve the quality of life of women and girls. Women participation in committees will also be encouraged and where any incidences of harassment and abuse, the responsible committees will ensure such cases are prevented and if they occur, they are successfully concluded.

## 3.4 Stakeholders from Government Agencies

This category of stakeholders encompasses the leading agencies responsible for overseeing the successful implementation of the LLL Project.

Table 4: Institutions and project implementation role

| Institution | Project implementation role |
| --- | --- |
| MAF-DOF | Overall PCU to take lead in facilitating and implementing activities related to protected area management, forestry, forest industry, protected areas and livelihood opportunities association with forest development. Responsible for management of all three forest categories: conservation, protection and production. |
| Protected Area Management Division (PAMD) under DOF | Has the legal mandate to manage PA, and efforts continue to raise the knowledge, skills, and abilities of the division. |
| MAF-DOFI | Coordinate with other Lao-WEN agencies to implement activities on forest and wildlife law enforcement. |
| NAFRI | Implement activity on germ plasm and other agronomic issues. Assist in relation to NTFPs and agro-biodiversity in multi-functional landscapes |
| MOIC | [work in progress] Implement activity under Component 1 to strengthen enabling environment for private sector participation in forest production, processing and downstream industries (furniture, lumber, pellets, etc.). |
| MAF-DALM | Land Use Planning, and land assessment and restoration |
| MONRE | [work in progress] Responsible for integrated spatial planning at large scale, monitoring implementation of the emerging new Land Law and land rights therein, reviewing and approving ESIAs and Strategic Environmental Assessment. |
| Environmental Police |  |
| MOICT | [work in progress] |
| MPI | Support sustainable private sector participation and partnerships in forestry and nature-based tourism. |
| Environment Protection Fund | To be determined |
| Other relevant ministries | To provide support in activities related to their respective fields. |
| Private Sector | In Lao PDR, forest plantation, wood industry development, and agricultural production and marketing are predominantly private sector activities. The private sector plays a vital role in a number of aspects to support the production sectors, through the provision of training, seminars, workshops on governmental regulations, technical assistance, research and extension, financial and other support to participant communities. Potentially companies can provide village development funds at district, village cluster and village levels. |
| Lao Women’s Union |  |
| Lao Front for National Construction | Mass organization in charge of ethnic policy |
| Lao National Tourism Administration | LNTA is a government organization (ministry level), subordinated to the Prime Minister’s Office. The main roles and responsibilities of the LNTA is to develop National Tourism Strategy for Lao PDR, set up policy, law, degrees, rules and regulations on tourism and hotel management, undertake marketing activities in order to promote tourism in Lao PDR, encourage human resource development for tourism and strengthen capacity building, use and monitor the Tourism Development and Promotion Fund, give permission to establish tourism business, warn, fine, and cancel the operations of tour operators, etc. |
| MoJ - Prosecutor |  |

## 3.5 Summary of Project Stakeholders Needs

The table below displays details on stakeholders characteristics, language needs, preferred notification  means and also specific needs stakeholders may have.

Table 5: Summary of Project Stakeholders Needs

| Stakeholder group | Key characteristics | Language needs | Preferred notification means | Specific needs |
| --- | --- | --- | --- | --- |
| Project Affected Parties | Community leaders, women, ethnic group, poor households, disabled | Ethnic language | Consultation meetings. Information leaflets and brochures Posters Focus Group Discussions Village meeting Village speakers Radio Information board Video | FPIC process Need facilitator in ethnic languages Involved women facilitators to target women Disaggregated FGD with vulnerable groups Gender disaggregated FDG Training |
| General public | Multi ethic population | Lao & English language | Press releases in the local media Social medias Website TV Radio Reports | Prior access to project information Lao language translation Target area, budget, main activities, stakeholders involved, community benefits Possibility to provide comments |
| Private sector | Multisectoral | Lao language, English language | Public notices Workshop Training Emails Whats App (WA) | Prior access to project information Lao language translation Opportunities of participation, modalities of private sector engagement |
| Development partners & donors | Multisectoral | Lao language, English language | Public notices Workshop Training Emails Information board | Prior access to project information Lao language translation Possibility to provide comments |
| CSOs | Expertise at field level | Lao, English | Public notices Workshop Training Emails Information board Whats App (WA) | Need to access project information prior to workshop and events Lao language translation Possibility to provide comments |
| Government agencies | Central, provincial and district level | Lao language | Public notices Workshop Training Emails Information board Whats App (WA) | Prior access to project information Lao language translation Offiicial documents |

# Stakeholder Engagement Program

Stakeholder engagement activities need to provide specific stakeholder groups with relevant information and opportunities to voice their views on topics that matter to them.

Stakeholder engagement is considered both a tool for ensuring good project management and a fundamental principle for guiding the procedure for identifying, assessing and managing environmental and social risks.

## 4.1 Purpose and Timing of Stakeholder Engagement Program

### Engagement during Project Preparation

The project will utilize various methods of engagement that will be used by the implementing agencies as part of their continuous interaction with the stakeholders. For the engagement process to be effective and meaningful, a range of techniques need to be applied that are specifically tailored to the identified stakeholder groups. Methods used for consulting with Government officials may be different from a format of liaising with the local communities (e.g. focus group discussions, displays and visuals with a lesser emphasis on technical aspects).

The Project will maintain on-going engagement with the national authorities, affected stakeholders and other interested parties to ensure that they are informed about the Project progress, that they receive information on the environmental and social performance, that they can provide feedback on the effectiveness of any mitigation and management measures and that they have the opportunity to raise any concerns or grievances.

Three main consultation sessions will be conducted during the preparation phase. The first consultation about the SEP and the ESCP and the second consultation about the ESMF and the CEF will take place in Vientiane. A third consultation will be conducted in one forest landscape area and will involve representatives from the communities and district offices.

Table 6: Engagement during project preparation

| Stakeholder consultation/ refinement & submission | Participants | Expected time frame |
| --- | --- | --- |
| Prepare stakeholder consultations | DoF, consultants/ SFP | June (week 1 & 2) |
| Stakeholder consultation 1 on SEP/ ESCP | National workshop with central level stakeholders & provincial representatives Remote participation for WB Email MAF Website | July (week 2) |
| Stakeholder consultation 2 on ESMF/ CEF | Central level stakeholders Provincial representatives Remotely for WB Email MAF Website | August (week 3) |
| Stakeholder consultation 3: in selected province/ landscape | District offices Village representatives | August (week 3) |
| Refine advanced drafts/ develop final versions | DoF, consultants/ SFP | September (week 1) |
| Submit final versions (ESCP, SEP, ESMF, CEF) to WB | Email MAF Website | September (week 1) |

### Engagement During Project Implementation

The LLL project will relay on sereval engagement techniques according to the type of stakeholders involved in the project implementation phase.

Table 7: Engagement During Project Implementation

| Involvement Techniques | Application and Approach | Stakeholder | Time frame |
| --- | --- | --- | --- |
| Information Board (Fact Sheets) | Create an information board containing LLL project information | Government, development agencies, CSOs, community level | Project Implementation Phase (commencing in Year 1 and ongoing) |
| Regular correspondence (via phone/WA/text message/email/others) | Build a communication platform such as WA group, Personal communication via either phone, text message, WA, email, or other communication devices. | DOF, government agencies, development partners, CSOs, community leaders | Project Implementation Phase (commencing in Year 1 and ongoing) |
| Public actions | Press release, social media, social medias, website, TV, radio | All stakeholders | Project planning, implementation and completion phase |
| Participative Public Consultation | Provide two-ways communication mechanism about the LLL project from the villageup to national level Facilitation for building trust among the stakeholders. Give an opportunity to the stakeholdersto provide feedback and opinions. Distribute non-technical project information to target communities. Facilitate meetings at village level using poster, film, pamphlet, etc. Record the discussion, comments/questions or responses conveyed | DOF, national level stakeholders, provincial and district stakeholders, private sector, development partners, CSOS, PSFM & VLD Teams, project affected persons | Project Planning Phase Project Implementation Phase Project Completion Phase |
| Formal meeting | Present information of LLL project to the stakeholders. Build trust and mutual respect among the stakeholders. Give an opportunity to the stakeholders to provide feedback and opinions. Distribute technical documents to the relevant groups. Record the discussion, comments/questions or responses conveyed | Government agencies, private sector, development partners, CSOs, community representatives | Project Implementation Phase Project Completion Phase |
| Workshop | Present information of LLL project to the stakeholders Facilitation for building trust among the stakeholders Avoid a long and boring “lecture” session Give an opportunity to the stakeholder group to provide feedback and opinions. Use the participative method (including interactive game) to facilitate a group discussion, to share opinions on many problems, to analyze information, and to develop a recommendation and strategy Record the discussion, comments/questions or responses conveyed | National level, provincial level, sub-community level (koumban or district level) | Project Implementation Phase Project Completion Phase |
| Focus Group Discussion (FGD) | Facilitate a smaller group consisting of 8 – 10 All participants share thier views and opinions on targeted thing. Design and facilitate a process in a participative manner Facilitation for building trust among the stakeholders Use key questions as guidelines for facilitating FGD Record the discussion, comments/questions or responses conveyed | Government agencies, develoment partners, villagers, women, ethnic group, vulnerable groups, CSOs | Project Planning Phase Project Implementation Phase Project Completion Phase |
| Interview | Collect views and opinions Facilitate the stakeholders to talk freely but confidentially about controversial and sensitive problems. Build a personal relation to the stakeholders Build trust through an attractive conversation Recording the interview Use local languages to ensure grassroot voices are heard and recorded | All / any stakeholder type | Project Planning Phase Project Implementation Phase Project Completion Phase |
| Field Survey | Collect opinions and views from each stakeholder Collect the primary data or the secondary data Record the data Develop a basic database to monitor the impact | All / any stakeholder type | Project Planning Phase Project Implementation Phase Project Completion Phase |

## 4.2 Proposed Strategy for Information Disclosure

As a standard practice, this SEP in English will be released for public review in accordance with Lao regulatory frameworks. Distribution of the disclosure materials will be done by making them available at venues and locations convenient for the stakeholders and places to which the public have unhindered access.

Electronic copies of the SEP will be placed on the website of the Bank and each implementing agencies. This will allow stakeholders with access to Internet to view information about the planned development and to initiate their involvement in the public consultation process. The web-site will be equipped with an on-line feedback feature that will enable readers to leave their comments in relation to the disclosed materials.

The mechanisms which will be used for facilitating input from stakeholders will include press releases and announcements in the media, notifications of the aforementioned disclosed materials to local, regional and national NGOs, relevant professional bodies as well as other interested parties

Brochure/leaflet for the Project will be developed and includes information about the Project in detail. Also, the brochure outlines the environmental and social impact assessment process and provide contact information (email, phone, postal address and fax) for the Public Relations Department of the Project Subcontractor for any grievances.

Table 8: Proposed Strategy for Information Disclosure

| Project stage | List of information to be disclosed | Methods proposed | Target stakeholders | Percentage reached | Responsibilities |
| --- | --- | --- | --- | --- | --- |
| Project Inception | ESCP, SEP, CEF, ESMF | Website Consultation workhop Grassroots consultation in selected landscape | Government agencies, CSOs, INGOs, Development partners, communities, private sector | 100% relevant agencies | Indufor, PS |
| Project Implementation | Updated project’s ESF instruments, Planning, budget, monitoring report, mid term review, Feedback of project consultations | Information leaflets, posters and brochures; audio-visual materials, social media and other direct communication channels such as mobile/ telephone calls, SMS, etc; Public notices; Electronic publications and press releases on the MAF websites; Press releases in the local media (both print and electronic); Consultation with vulnerable and marginalized groups using mobile/ telephone calls, SMS, etc. in a culturally appropriate manner; training and meetings, household interviews. | Project affeted parties Other interested parties | 100% communities reached 60% households in each community 50% participants are women | PSFM, VLD teams |
| PSFM | Project information Forest Management Plan | Information leaflets Posters IEC materials Boards Gender disaggregated FGD Process in ethnic languages Training Grievance Redress Mechanisms | Project affected parties Communities Ethnic groups Women Customary leaders Vunlerable households | 100% communities reached 60% households in each community 50% participants are women | PSFM team LFNC LWU |
| VLD | Project information Community Action Plan | Information leaflets Posters IEC materials Gender disaggregated FGD Process in ethnic languages Training Grievance Redress Mechanisms | Project affeted parties Communities Ethnic groups Women Customary leaders Vunlerable households | 100% communities reached 60% households in each community 50% participants are women | VLD team LFNC LWU |
| Nature Based Tourism | Project information NBT plan | Information leaflets Posters IEC materials Gender disaggregated FGD Process in ethnic languages Training Grievance Redress Mechanisms | Project affeted parties Communities Ethnic groups Women Customary leaders Vunlerable households | 100% communities reached 60% households in each community 50% participants are women | DOICT LFNC LWU DONRE |
| Supervision & Monitoring | Monitoring reports, yearly reports | Field visit Consultartion Workshop | Project affeted parties Other interested parties | Project’s outcomes, overall progress and major achievements | Virtual roundtable discussions; Press releases; Press conferences; Public meetings; Reports; MAF website |
| Project Close Out | Enf of project report | National workshop | Government Project affeted parties Other interested parties | Project exit strategy Dissemination final reports | Consultation meetings; information leaflets, posters and brochures; audio-visual materials, social media; Electronic publications and press releases on the MAF websites; Press releases in local media |

Various means of communication and informaton sharing will also be used among stakeholders.

Table 9: Means of communication

| Stakeholder Group | Project Information Shared | Means of communication/ disclosure |
| --- | --- | --- |
| Project Affected Parties | Stakeholder Engagement Plan; Public Grievance Procedure; Regular updates on Project development. | Public notices. Electronic publications and press releases on the Project web-site. Dissemination of hard copies at designated public locations. Press releases in the local media. Consultation meetings. Information leaflets and brochures. Separate participatory focus group meetings with vulnerable groups, as appropriate. |
| Non-governmental Organizations | Stakeholder Engagement Plan; Public Grievance Procedure; Regular updates on Project development. | Public notices. Electronic publications and press releases on the project web-site. Dissemination of hard copies at designated public locations. Press releases in the local media. Consultation meetings and workshops. Information leaflets and brochures |
| Ministries, Departments and Agencies | Stakeholder Engagement Plan; Regular updates on Project development; Additional types of Project’s information if required for the purposes of regulation and permitting. | Dissemination of hard copies of the ESMF, ESMP package, and SEP at municipal administrations. Project status reports. Meetings, multi-stakeholder workshops and round tables. |
| Development partners | Stakeholder Engagement Plan; Public Grievance Procedure; Regular updates on Project development. | Electronic publications and press releases on the project web-site. Project status reports. Meetings, multi-stakeholder workshops and round tables. |
| Private sector | Stakeholder Engagement Plan; Public Grievance Procedure; Updates on Project development and tender/procurement announcements. | Electronic publications and press releases on the Project web-site. Information leaflets and brochures. Procurement notifications. |
| Project staff | Stakeholder Engagement Plan; CEF, operation manual, etc. | Staff handbook. Email updates covering the Project staff and personnel. Regular meetings with the staff. Posts on information boards in the offices and on site. Reports, leaflets. |

## 4.3 Proposed Strategy for Consultation

A range of tools was used and will continue to be used for the stakeholder engagement as part of this Project. These include household surveys, focus groups, community level questionnaires, leaflets and key informant discussions. Stakeholder engagement will continue using these employed mechanisms as required ensuring efficient and effective engagement throughout the life of the project.

Specific methods will vary across different stakeholder groups and stakeholder engagement with vulnerable and minority groups will use specifically designed mechanisms, as needed.

The current ontext of Covid 19 outbreak affects the Bank requirements for public consultation and stakeholder engagement. In the case of projects under preparation and stakeholder engagement is about to commence or is ongoing, such as in the project E&S planning process, stakeholder consultation and engagement activities should not be deferred, but rather designed to be fit for purpose to ensure effective and meaningful consultations to meet project and stakeholder needs following the Bank’s Technical Note on Public Consultations and Stakeholder Engagement in WB-supported operations when there are constraints on conducting public meetings dated March 20, 2020. The note advises to avoid public gatherings (taking into account national restrictions), including public hearings, workshops and community meetings, and minimize direct interaction between project agencies and beneficiaries / affected people, make all reasonable efforts to conduct meetings through online channels, including webex, zoom and skype meetings and rely more on social media and online channels. In situations where online interaction is challenging, information can be disseminated through digital platform (see annex 1).

At central level

Consultation will take place among relevant Ministries with the coordination of DOF as the lead agency. Besides the line agencies, other groups interested in forest management, livelihood develoment and ecotourism will be invited to consultations. Among others: development partners, private investors (mainly in forest plantation, agri-business and ecotourism), Civil Society Organizations (CSOs) including international NGOs, National University of Laos (NUOL) and the GoL’s mass organizations: Lao Women’s Union (LWU) and Lao Front for National Construction (LFNC).

Consultation may take the form of face-to-face meetings and issuance of official letters (submitted at least two weeks ahead of the consultations) to inform affected and interested stakeholders of the purpose of the consultation event.

At provincial and district level

Consultations at province and district level will ensure participation of representatives the line agencies and mass organizzations at province and district, plus other relevant stakeholders coming from the civil society, academia or private sector.

Consultation may take the form of face-to-face meetings and issuance of official letters (submitted at least two weeks ahead of the consultations) to inform affected and interested stakeholders of the purpose of the consultation event.

Contents to be discussed during consultation meetings

The project has to prepare in advance a document that summarize the purpose of the main project, its key activities, as well as the purpose of the consultation, including its specific activities that plan to be done. Potential impacts and risks of the main projects, with a focus on the potential impacts and risks resulting from implementation of the activities which the SEP is intended for. Measures designed to avoid such adverse impact and risks, as well as mitigations measures (in case adverse impact cannot me avoided) will be presented and discussed with all the participants.

## 4.4 Proposed Strategy to Incorporate the View of Vulnerable Groups

### Free, Prior and Informed Consent FPIC

Stakeholder engagement practices should adhere to the requirements and are expected to adhere to standards outlined in key relevant international instruments and to uphold the principle of free, prior and informed consent (FPIC) as stated in the UN Declaration on the Rights of Indigenous Peoples (UNDRIP).

In accordance with ESS7, FPIC of the affected Local Communities is required in circumstances in which the project or project activities will: (a) have adverse impacts on land and natural resources subject to traditional ownership or under customary use or occupation; cause relocation of Local Communities from land and natural resources subject to traditional ownership or under customary use or occupation; or (c) have significant impacts on  Local Communities’ cultural heritage that is material to the identity and/or cultural, ceremonial, or spiritual aspects of the affected Local Communities’ lives.

Free, Prior and Informed Consent (FPIC) is the collective right of ethnic peoples to participate in decision-making and to give or withhold their consent to activities affecting their lands, territories and resources or rights in general. Consent must be freely given, obtained prior to implementation of activities and be founded upon an understanding of the full range of issues implicated by the activity or decision in question; hence the formulation: free, prior and informed consent. The project will build upon the lessons learned from SUFORD and CLIPAD who have piloted piloting FPIC.

- All project beneficiaries, regardless of their ethnic group or social status, shall be engaged in a culturally relevant way on the basis of a free, prior, and informed consultation aimed at establishing broad-based and sustainable community support for the project

Engagement requires that information is available in the appropriate language(s)

Community participates in and benefits from forest management and livelihood development activities

### Engaging with Women

Climate change affects everybody; however, its impacts are distributed differently. Women have relatively higher dependence on natural resources for subsistence and livelihood. Therefore, women are more likely to be vulnerable to the impacts of climate variations and climate change induced natural disasters. Rural women and men have specific roles, rights, and responsibilities that determine their access to resources and its usage, which translates into varying vulnerability and decision-making power for women and men.

Women’s inclusion is a means to achieve gender equality in sustainable management of forests and livelihood development activitites. Women’s inclusion denotes to their meaningful participation that goes beyond the number of men and women and addresses the gender-gaps for them to have opportunities and choices. Gender equality is important for both performance and safeguard reasons. Addressing gender gaps requires integration of practical and strategic needs of women into LLL project activities at the operational level of subnational planning and broader sustainable development and poverty strategies.

Gender mainstreaming can be defined as a process to integrate perspectives and roles of both men and women, as an integral part in designing, implementing, monitoring and evaluating plans, policies and programs, so that both men and women can engage equally and benefit equitably. Thus, gender mainstreaming goes beyond simply increasing women’s participation - it means recognizing and integrating the experiences, knowledge, and interests of women and men in the decision-making process. In the development context, it means identifying and applying the gender-dimension in goals, strategies, and actions of the development agenda, so that both women and men can influence, participate in, and benefit from development processes.

From an institutional perspective, both the Lao Women Union (LWU) and the Committee for the Advancement of Women (NCAW) are involved in the project.

The project commits to follow the National standard from NCAW for participation requirement of women in Agriculture and Forestry ensure that women participate, in decision making & get benefits. The LWU is also involved up to the community level. During consultation involving communities’ representatives, village level representative of the LWU will be invited from each village and gender disaggregated FGD to ensure women voices are heard and recorded.

### Engaging with Ethnic Groups

LLL Project has the potential to deliver several benefits to ethnic peoples and other forest-dependent communities, including the sustainable management of biodiversity, the provision of alternative livelihoods, equitable sharing of revenues generated from emissions reductions, etc. However, if not done appropriately, it also presents risks to rights, livelihoods, culture, biodiversity, etc. For the project to succeed, these risks have to be identified, reduced and mitigated, and stakeholders have to be involved at the project/program formulation as well as the preparation and implementation stages in order to ensure that the LLL Project respect ethnic  peoples’ rights and comply with relevant international obligations.

There are several modalities of involvement of ethnic group in the LLL Project. This start upstream at institutional level by involving the Lao Front for National (LFNC), a mass organization as well as the Department of Ethic Affairs (DOEA) under the Ministry of Home Affairs (MOHA) both are in charge of ethnic policy issues.

It is not yet possible to determine which ethnic groups will be involved in the consultation at field level as the hotspots are yet to be determined. Nevertheless, we have already inventoried all ethnic groups in all villages in the whole country using the data from the 2015 National census provided by the National Statistic Center (NSC). Once the landscape are defined, the provincial steering committee will recruit ethnic facilitators that will be trained and lead the consultation with village representative at kumban level. The Poverty Reduction Fund (PRF) has recruited kumban ethnic facilitators in 42 districts in 10 provinces those could be involved as well as the ethnic staff working in the VLD or PFSM district team supported by SUFORD. There are over 20 ethnic groups represented. Customary leaders from each community will be involved in the consultation at kumban level. In areas where CSOs are involved, they will also contribute to facilitate and bridge linguistically and culturally with the communities.

## 4.5 Timelines

Prior to any events or consultations, the target participants will be informed in advance to ensure full availability. During each project activities at field level the project will provide relevant information in local languages to ensure that the target auditory is informed prior to taking any decision.

The first central level consultation (including participating provinces) on the SEP-ESMP is planned for July 17 at the Deparrtment of Forestry. The second central level consultation on the ESMF-CEF (including participating provinces) will take place the last week of August at DOF. The third consultation also planned for the last week of August will take place in one selected province or landscape area and will involve district representartives and community delegates. The ESCP, SEP, ESMF and CEF will be refined according to the consultation and the final  versions are intended to be sumbitte dto the WB the first week of September 2020.

## 4.6 Review of Comments

From a general point of view, during each event, an attendance lists will be taken ensuring that age, gender, ethnicity and social position are recorded each participant. The team will also record people’s concerns, the content of the activity, main decisions made, plans agreed, etc. During the preparation phase, SEP, ESCP, CEF and ESMP will be shared with project stakeholders in advance to ensure that all have sufficient time to acknowledge the content and formulate comments, feedback and suggestions. Sessions will be organized to provide stakeholders with feedback on how the comments have been taken into consideration.

## 4.7 Future Phases of Project

Stakeholders will be kept informed as the project develops, including reporting on project environmental and social performance and implementation of the SEP and Grievance Redress Mechanism.

# 5. Resources and Responsibilities for Implementing Stakeholder Engagement Activities

## 5.1 Resources

The Department of Forestry (DOF) will be in charge of organizing stakeholder engagement activities and provide the necessary financial and human resources to undertake stakeholder engagement. A dedicated budget of 96,725 USD  is estimated for implementtaion of SEP and stakeholders engagement activities excluding the cost of consultations which are embedded in  in various project activities e.g village land use planning livelihood planning exercises, GRM involving direct and indirect stakeholers throughout the project implementation periodManagement Functions and Responsibilities (see annex 4).

## 5.2 Management functions and responsibilities

The Government of Lao PDR would implement the project using existing institutions at central, provincial, district and village levels, based on their legal mandates. A Project Coordination Unit (PCU) located at DOF provide project services to the ministries and provincial institutions implementing specific activities financed by or linked to the operation. Each institution would have a dedicated project implementation team networked to the PCU to form a robust multisector team that regularly exchanges relevant information across institutions and sectors.

# 6. Grievance Redress Mechanisms

In compliance with the World Bank’s ESS10 requirement, a specific grievance mechanism will be set-up for the project. Dedicated communication materials (GRM pamphlets, posters) will be created to help local residents familiarize themselves with the grievance redress channels and procedures.

A GRM guidebook/manual will also be developed and suggestion boxes installed in each affected municipality and village. In order to capture and track grievances received under the project, a dedicated GRM Management Information System/database is planned. GRM committees at the municipal level will benefit from training on how to receive, respond to, address and close grievances in line with best international practices. Internal GRM training will also take place for project staff. The LLL project’s website will include clear information on how feedback, questions, comments, concerns and grievances can be submitted by any stakeholder and will include the possibility to submit grievances electronically.

## 6.1 Access to Justice and Grievance Redress Mechanism in Lao PDR

The GRMs are organizational systems and resources established by national government agencies to receive and address concerns about the impact of their policies, programs and operations on external stakeholders.

GRMs are intended to complement, not replace, formal legal channels for managing grievances. These mechanisms are not intended to replace the judiciary or other forms of legal recourse. GRMs act as recourse for situations in which, despite proactive stakeholder engagement, some stakeholders have a concern about the organization’s actual or potential impacts on them.

According to the Lao PDR legal framework, Article 13 of Decree 84/PM requires a project to establish an effective mechanism for grievance resolution. As projects are responsible for carrying out project works that are likely the source of grievances they are best placed to respond to and resolve grievances in the most timely and acceptable method.

Lao citizens’ access to justice is guaranteed by Section 41 of the 2015 revised national Constitution.

ພົນລະເມືອງລາວ ມີສິດສະເໜີ, ຮ້ອງຟ້ອງ ແລະ ຮອ້ງຂໍຄວາມເປັນທຳຕໍ່ອົງການທີ່ກ່ຽວ ຂອ້ງກ່ຽວກັບບັນຫາທີ່ພົວພັນເຖິງສິດ ແລະ ຜົນປະໂຫຍດຂອງສ່ວນລວມ ຫຼື ສິດ ແລະ ຜົນປະໂຫຍດ ສະເພາະຂອງຕົນ. ຄຳສະເໜີ, ຄຳຮ້ອງຟ້ອງ ແລະ ຄຳຮອ້ງຂໍຄວາມເປັນທຳ ຂອງພົນລະເມືອງ ຕ້ອງໄດ້ຮັບການພິຈາລະນາ ແລະ ແກ້ໄຂຕາມທີ່ໄດ້ກຳນົດໄວ້ໃນກົດໝາຍ.

This section states that any dispute should be resolved amicably using existing “customary and traditional” practices and mutual agreement involving the concerned disputing parties and other concerned stakeholders with, where appropriate, the assistance of the village administration, traditional authorities, and Government officers as third parties.

The Village Mediation Unit has been a semi-formal justice mechanism designed to achieve mediated outcomes based on principles of national (state) law, but also take into account ‘good’ local traditions and practice. The VMU has additional functions, such as assisting the village administration to enhance knowledge of, and compliance with, state laws in the village. It also coordinates with judicial and other relevant bodies. The Ministry of Justice (MoJ) has promulgated a new Decree 404 to strengthen this village-level institution, which now changes its name from Village Mediation Unit (VMU) (nouay kay kia khan ban) to Village Mediation Committee (VMC) (khana kae khay kho khat nieng khan ban).

In the past, the VMU was set up for 3 years, but now VMC members are elected on a permanent basis. The VMC is composed of 7 permanent members including the village head of the Lao Women’s Union (LWU) to ensure that women voices are heard. The new decree set up new procedure (10 main steps for conflict mediation) and new regulations. Capacity building activities to strengthen VMC members conducted by the Ministry of Justice and sometimes in collaboration with international agencies focus on legal literacy and mediation skills.

If the “traditional and customary” approach in resolving the dispute fails, there are three possible paths that citizens can follow to seek redress of any grievance with Lao State institutions, including: 1) admistrative (ທາງບໍລິຫານ), 2) judicial (ທາງຕຸລາການ), and 3) legislative (ທາງນິຕິບັນຍັດ). A fourth path is through Party internal audit and mass organizations, i.e., the Lao Front for National Construction (LFNC, or “the Front”), the Lao Women’s Union (LWU), or the Lao Youth Union (LYU).

Figure 1	LLL Grievance Redress Mechanism

Usually grievances in Lao PDR follow the adminstrative structure from grassroots to the central level. Thus the initial points of contact between the grievant and a project consist of working first with village officials, then if necessary, with district, provincial, and finally central level.

According to an Access to Justice Survey carried out by UNDP and the Lao Bar Association (LBA) in 2009, people were twice as likely to use a customary mechanism as they were the VMU - and five times more likely than they were to go to court.

In addition to these four paths for grievance redress, the LLL project will use a fifth path for grievances related to the project or sub-projects. The remainder of this section describes this mechanism, which uses Provincial and National Steering committees to review grievances.

Consultations will be done with a wider range of stakeholders as part of future consultations on the ESF requirement, i.e., the Environmental and Social Management Framework, and the Community Engagement Framework.

## 6.2 Key Fundamentals for GRM

Conflicts may result from project activities. They will be resolved following a grievance mechanism that is based on the following key fundamentals:

- Rights and interests of impacted people, communities’, workers and others associated with, or impacted by the project are protected.

- Concerns of project participants arising from the project implementation process are adequately addressed and in a prompt and timely manner.

- Entitlements or livelihood support for project participants are provided on time and in accordance with the Government and World Bank safeguard policies.

- Project participants are aware of their rights to access grievance procedures free of charge.

- The grievance mechanism should be in line with existing policies, strategies, and regulations on grievances as defined by GOL, which require project owners/developers to set up grievance mechanisms starting from the village level, and also follow recent legislation under Decision No. 08/MOJ, dated 22 February 2005 that seeks to strengthen conflict resolution at the grassroots level, by establishing Village Mediation Committee (VMC). With respect to resettlement and complementation, GOL Decree 84/PM requires that the project owners, or developers, put in place a fair and equitable grievance redress mechanism. Specific requirements are described in Part VI of the Decree’s Implementing Regulations, and as part of the Technical Guidelines in more detail. Decree 84/PM determines that the prime responsibility for grievance resolution lies with the Project proponent, that are responsible for carrying out the project which may be the source of grievances (such as the access restrictions, entitlements, etc.) and as such, they are best placed to respond to and resolve grievances in the most timely and acceptable method. Other legal instruments related to grievance redress issues are indicated in Annex 1.

## 6.3 Key Principles Guiding the Design of a Grievance Redress Mechanism

The LLL Project Grievance Redress Mechanism should incorporate the following key principles. It should be:

a. Legitimate: enabling trust from the stakeholder groups for whose use they are intended, and being accountable for the fair conduct of grievance processes.

b. Accessible: being known to all stakeholder groups for whose use they are intended, and providing adequate assistance for those who may face particular barriers to access

c. Predictable: providing a clear and known procedure with an indicative timeframe for each stage, and clarity on the types of process and outcome available and means of monitoring implementation.

d. Equitable: seeking to ensure that aggrieved parties have reasonable access to sources of information, advice and expertise necessary to engage in a grievance process on fair, informed and respectful terms.

e. Transparent: keeping parties to a grievance informed about its progress, and providing sufficient information about the mechanism’s performance to build confidence in its effectiveness

f. Rights compatible: ensuring that outcomes and remedies accord with internationally recognized human rights.

g. Enabling continuous learning: drawing on relevant measures to identify lessons for improving the mechanism and preventing future grievances and harms.

h. Based on engagement and dialogue: consulting the stakeholder groups for whose use they are intended on their design and performance and focusing on dialogue as the means to address and resolve grievances.

## 6.4 Details of Grievance Processing from Village to Central Level

### Step 1: Village Level

A grievant (individual or group of villagers) who has been believes that they have suffered a (perceived or actual) negative impact from the LLL project or program implementation should fill out a grievance form and submit it to the Village Mediation Unit. (See grievance registration forms).

A formal submission of the grievance is the appropriate complaint mechanism. For ethnic minority or non-literate people, a verbal grievance shall be documented by the VMC, using the form provided and signed, or fingerprinted, by the Grievant for processing.

After receiving the written complaint, the VMC will document the grievance by using the Initial data collection form provided and signed, or fingerprinted, by the grievant for processing. The VMC will keep the Village Grievance Logbook.

The VMC will be required to provide immediate confirmation of receiving a grievance, and should complete an investigation within 14 days of receipt. Then, within 5 days after receipt of the grievance the VMC should meet the Grievant to discuss (mediate) the grievance and advise the complainant of the outcome. If the grievance is either a valid project related grievance that requires investigation and action or compensation, or if the Complainant is not satisfied with the response, the issue is transferred within one month to the next level, to the District focal point or Grievance Committee (DFP-DGC), for further action.

The facts are then reviewed through a VMC hearing attended by the VMC Head and at least two members of the VMC, the Grievant and up to two witnesses provided by the Grievant (Form).

In the event that a grievance related to a Physical Cultural Resource, a Culturally Significant Area, or salvage logging is submitted, the VMC shall report the grievance to the District focal point or Grievance Committee immediately.

### Step 2: District Level

Grievances that cannot be resolved at the village level will be brought to the District focal point or Grievance Committee (DFP-DGC) that will have 30 days after the receipt to review all available information from the investigation and analyze and investigate each case. Within 30 days, the Committee invites the Grievant to discuss the grievance, and the Grievant is informed of the outcome of the investigation and the decision.

If the Grievant is satisfied with the outcome, the issue is closed, and the Grievant provides a signature, or fingerprint, as acknowledgement of the decision. If the Grievant is not satisfied with the outcome, the Grievant may submit an appeal to the Committee if there is additional relevant information for reconsideration.

Within 14 days the Committee will both collect facts and reinvestigate and will invite the Grievant to discuss the appeal, and the Grievant will be informed of the outcome of the investigation and the decisions made. If the Grievant is still dissatisfied with the outcome, he, she, or they can then submit the grievance to the Provincial REDD+ Task Force. The District Grievance Committee will also be in charge of compiling all grievances into a District Grievance logbook.

### Step 3: Provincial Level

Strong or unresolved grievances, such as land grabbing cases, will be referred to the Provincial Steering Committee (PSC) that acts as the secretariat and coordinating body for project related issues at provincial level. One member of this office will be designated as the focal point for receiving any grievances. The Provincial Focal Point (PFP) will present the case to the Provincial Steering Committee (PSC) that will be chaired by the Vice Governor of the province. Members of this committee will include the Deputy District Governors of all participating districts, division heads of participating line agencies, and representatives of LWU and LNFC. The PRO will compile all grievances into a Provincial Grievance logbook.

If the Grievant is still dissatisfied with the outcome, the Grievant then may the grievance to the National Steering Committee.

### Step 4: Central Level

Grievances that cannot be solved at the provincial level will be sent to the National Steering Committee within DOF. The Central Focal Point (CFP) will send the grievance to the National Steering Committee, chaired by the Deputy Minister of the Ministry of Agriculture and Forestry. Members include DG/DDG level representatives of participating agencies in various ministries (MAF, MONRE, MOIC, MPI, etc.), as well as national leaders of mass organizations like the LNFC and the Lao Chamber of Commerce.

It should be noted that at each level, the grievants are allowed to report their grievances directly to the administrative, judicial, or legislative system, i.e., the provincial or National Assembly, or to seek redress through the Party system.

## 6.5 Steps Process to Redress Grievances

The LLL Grievance Resolution Mechanisms proposes a 7-step process to redress grievance (for details see Annex 2). GRM acts as recourse for situations in which, despite proactive stakeholder engagement, some stakeholders have a concern about the organization’s actual or potential negative impacts on them.

Figure 2: Steps process to redress grievances

# 7. Monitoring and Reporting

The Stakeholder Engagement Plan will be periodically revised and updated as necessary in the course of capacity building program implementation in order to ensure that the information presented herein is consistent and is the most recent, and that the identified stakeholders and methods of engagement remain appropriate and effective in relation to the project context and specific stages of the implementation. Any major changes to the project related activities and to its schedule will be duly reflected in the SEP.

## 7.1 Involvement of Stakeholders in Monitoring Activities

In order to address any potential project risks, and also to give participating villagers opportunities to suggest any measures that may enhance project benefits and further strengthen sustainability of affected people’s livelihood, the project will carry out Participatory Monitoring and Evaluation (M&E). Those villagers who are negatively affected by the project, especially vulnerable groups, will be given opportunities to voice the concerns they may have or the hardships they may be experiencing. Participatory monitoring is an essential tool for developing community “ownership” of a project, to assess how their plans, customary regulations, etc. are being implemented, and to learn how to improve.

## 7.2 Reporting Back to Stakeholder Groups

The SEP will be periodically revised and updated as necessary in the course of project implementation in order to ensure that the information presented herein is consistent and is the most recent, and that the identified methods of engagement remain appropriate and effective in relation to the project context and specific phases of the development. Any major changes to the project related activities and to its schedule will be duly reflected in the SEP.

Monthly summaries and internal reports on public grievances, enquiries and related incidents, together with the status of implementation of associated corrective/preventative actions will be collated by responsible staff and referred to the senior management of the project. The monthly summaries will provide a mechanism for assessing both the number and the nature of complaints and requests for information, along with the Project’s ability to address those in a timely and effective manner. Information on public engagement activities undertaken by the Project during the year may be conveyed to the stakeholders in two possible ways:

- Publication of a standalone annual report on project’s interaction with the stakeholders.

- A number of Key Performance Indicators (KPIs) will also be monitored by the project on a regular basis, including the following parameters:

number of public hearings, consultation meetings and other public discussions/forums conducted annually;

frequency of public engagement activities;

number of public grievances received monthly and number of those resolved within the prescribed timeline; and

number of press materials published/broadcasted in the local, regional, and national media.

# Annex

## Annex 1: Technical Note: Public Consultations and Stakeholder Engagement in WB-supported operations when there are constraints on conducting public meetings March 20, 2020

With the outbreak and spread of COVID-19, people have been advised, or may be mandated by national or local law, to exercise social distancing, and specifically to avoid public gatherings to prevent and reduce the risk of the virus transmission. Countries have taken various restrictive measures, some imposing strict restrictions on public gatherings, meetings and people’s movement, and others advising against public group events. At the same time, the general public has become increasingly aware and concerned about the risks of transmission, particularly through social interactions at large gatherings.

These restrictions have implications for World Bank-supported operations. In particular, they will affect Bank requirements for public consultation and stakeholder engagement in projects, both under implementation and preparation. WHO has issued technical guidance in dealing with COVID-19, including: (i) Risk Communication and Community Engagement (RCCE) Action Plan Guidance Preparedness and Response; (ii) Risk Communication and Community engagement (RCCE) readiness and response; (iii) COVID-19 risk communication package for healthcare facilities; (iv) Getting your workplace ready for COVID-19; and (v) a guide to preventing and addressing social stigma associated with COVID-19. All these documents are available on the WHO website through the following link: https://www.who.int/emergencies/diseases/novel-coronavirus-2019/technical-guidance.

This Note offers suggestions to World Bank task teams for advising counterpart agencies on managing public consultation and stakeholder engagement in their projects, with the recognition that the situation is developing rapidly and careful regard needs to be given to national requirements and any updated guidance issued by WHO. It is important that the alternative ways of managing consultation and stakeholder engagement discussed with clients are in accordance with the local applicable laws and policies, especially those related to media and communication. The suggestions set out below are subject to confirmation that they are in accordance with existing laws and regulations applying to the project.

Investment projects under implementation. All projects under implementation are likely to have public consultation and stakeholder engagement activities planned and committed as part of project design. These activities may be described in different project documents, and will involve a variety of stakeholders. Commonly planned avenues of such engagement are public hearings, community meetings, focus group discussions, field surveys and individual interviews. With growing concern about the risk of virus spread, there is an urgent need to adjust the approach and methodology for continuing stakeholder consultation and engagement. Taking into account the importance of confirming compliance with national law requirements, below are some suggestions for task teams’ consideration while advising their clients:

Task teams will need to review their project, jointly with the PMUs, and should:

• Identify and review planned activities under the project requiring stakeholder engagement and public consultations.

• Assess the level of proposed direct engagement with stakeholders, including location and size of proposed gatherings, frequency of engagement, categories of stakeholders (international, national, local) etc.

• Assess the level of risks of the virus transmission for these engagements, and how restrictions that are in effect in the country / project area would affect these engagements.

• Identify project activities for which consultation/engagement is critical and cannot be postponed without having significant impact on project timelines. For example, selection of resettlement options by affected people during project implementation. Reflecting the specific activity, consider viable means of achieving the necessary input from stakeholders (see further below).

• Assess the level of ICT penetration among key stakeholder groups, to identify the type of communication channels that can be effectively used in the project context.

Based on the above, task teams should discuss and agree with PMUs the specific channels of communication that should be used while conducting stakeholder consultation and engagement activities. The following are some considerations while selecting channels of communication, in light of the current COVID-19 situation:

• Avoid public gatherings (taking into account national restrictions), including public hearings, workshops and community meetings;

• If smaller meetings are permitted, conduct consultations in small-group sessions, such as focus group meetings If not permitted, make all reasonable efforts to conduct meetings through online channels, including webex, zoom and skype;

• Diversify means of communication and rely more on social media and online channels. Where possible and appropriate, create dedicated online platforms and chatgroups appropriate for the purpose, based on the type and category of stakeholders;

• Employ traditional channels of communications (TV, newspaper, radio, dedicated phone-lines, and mail) when stakeholders to do not have access to online channels or do not use them frequently. Traditional channels can also be highly effective in conveying relevant information to stakeholders, and allow them to provide their feedback and suggestions;

• Where direct engagement with project affected people or beneficiaries is necessary, such as would be the case for Resettlement Action Plans or Indigenous Peoples Plans preparation and implementation, identify channels for direct communication with each

affected household via a context specific combination of email messages, mail, online platforms, dedicated phone lines with knowledgeable operators;

• Each of the proposed channels of engagement should clearly specify how feedback and suggestions can be provided by stakeholders;

• An appropriate approach to conducting stakeholder engagement can be developed in most contexts and situations. However, in situations where none of the above means of communication are considered adequate for required consultations with stakeholders, the team should discuss with the PMU whether the project activity can be rescheduled to a later time, when meaningful stakeholder engagement is possible. Where it is not possible to postpone the activity (such as in the case of ongoing resettlement) or where the postponement is likely to be for more than a few weeks, the task team should consult with the OESRC to obtain advice and guidance.

Investment projects under preparation. Where projects are under preparation and stakeholder engagement is about to commence or is ongoing, such as in the project E&S planning process, stakeholder consultation and engagement activities should not be deferred, but rather designed to be fit for purpose to ensure effective and meaningful consultations to meet project and stakeholder needs. Some suggestions for advising clients on stakeholder engagement in such situations are given below. These suggestions are subject to the coronavirus situation in country, and restrictions put in place by governments. The task team and the PMU should:

• Review the country COVID-19 spread situation in the project area, and the restrictions put in place by the government to contain virus spread;

• Review the draft Stakeholder Engagement Plan (SEP, if it exists) or other agreed stakeholder engagement arrangements, particularly the approach, methods and forms of engagement proposed, and assess the associated potential risks of virus transmission in conducting various engagement activities;

• Be sure that all task team and PIU members articulate and express their understandings on social behavior and good hygiene practices, and that any stakeholder engagement events be preceded with the procedure of articulating such hygienic practices.

• Avoid public gatherings (taking into account national restrictions), including public hearings, workshops and community meetings, and minimize direct interaction between project agencies and beneficiaries / affected people;

• If smaller meetings are permitted, conduct consultations in small-group sessions, such as focus group meetings. If not permitted, make all reasonable efforts to conduct meetings through online channels, including webex, zoom and skype meetings;

• Diversify means of communication and rely more on social media and online channels. Where possible and appropriate, create dedicated online platforms and chatgroups appropriate for the purpose, based on the type and category of stakeholders;

• Employ traditional channels of communications (TV, newspaper, radio, dedicated phone-lines, public announcements and mail) when stakeholders do not have access to online channels or do not use them frequently. Such channels can also be highly effective in conveying relevant information to stakeholders, and allow them to provide their feedback and suggestions;

• Employ online communication tools to design virtual workshops in situations where large meetings and workshops are essential, given the preparatory stage of the project. Webex, Skype, and in low ICT capacity situations, audio meetings, can be effective tools to design virtual workshops. The format of such workshops could include the following steps:

o Virtual registration of participants: Participants can register online through a dedicated platform.

o Distribution of workshop materials to participants, including agenda, project documents, presentations, questionnaires and discussion topics: These can be distributed online to participants.

o Review of distributed information materials: Participants are given a scheduled duration for this, prior to scheduling a discussion on the information provided.

o Discussion, feedback collection and sharing: Participants can be organized and assigned to different topic groups, teams or virtual “tables” provided they agree to this.

oGroup, team and table discussions can be organized through social media means, such as webex, skype or zoom, or through written feedback in the form of an electronic questionnaire or feedback forms that can be emailed back.

o Conclusion and summary: The chair of the workshop will summarize the virtual workshop discussion, formulate conclusions and share electronically with all participants.

• In situations where online interaction is challenging, information can be disseminated through digital platform (where available) like Facebook, Twitter, WhatsApp groups, Project weblinks/ websites, and traditional means of communications (TV, newspaper, radio, phone calls and mails with clear description of mechanisms for providing feedback via mail and / or dedicated telephone lines. All channels of communication need to clearly specify how stakeholders can provide their feedback and suggestions.

• Engagement with direct stakeholders for household surveys: There may be planning activities that require direct stakeholder engagement, particularly in the field. One example is resettlement planning where surveys need to be conducted to ascertain socioeconomic status of affected people, take inventory of their affected assets, and facilitate discussions related to relocation and livelihood planning. Such survey activities require active participation of local stakeholders, particularly the potentially adversely affected communities. However, there may be situations involving indigenous communities, or other communities that may not have access to the digital platforms or means of communication, teams should develop specially tailored stakeholder engagement approaches that will be appropriate in the specific setting. The teams should reach out to the regional PMs for ENB and Social Development or to the ESSA for the respective region, in case they need additional support to develop such tailored approaches.

• In situations where it is determined that meaningful consultations that are critical to the conduct of a specific project activity cannot be conducted in spite of all reasonable efforts on the part of the client supported by the Bank, the task team should discuss with the client whether the proposed project activities can be postponed by a few weeks in view of the virus spread risks. This would depend on the COVID-19 situation in the country, and the government policy requirements to contain the virus spread. Where it is not possible to postpone the activity (such as in the case of ongoing resettlement) or where the postponement is likely to be for more than a few weeks, the task team should consult with the OESRC to obtain advice and guidance.

## Annex 2: Lao PDR Legal Instruments Related to Grievance Redress

CONSTITUTION

Constitution of the Lao PDR, No. 214/Gov. 15 December 2015 allows all country citizens to have the right to file grievances (complaints) and seek resolutions by various governmental entities.

LAWS

Law on Local Administration No 47 National Assembly, 21 October, 2003 indicates responsibility of the village headman on solving local conflicts.

Land Law No 04/NA, 21 October 2003 states that governmental authorities responsible for land management also has a conflict resolution role.

Law on Civil Procedures No 02, National Assembly, 15 May, 2004 explains that Village Mediation Unit can mediate minor disputes

State Property Law No 72 National Assembly, 12 October, 2004 gives details on what types of organization to deal with criminal or administrative conflicts

Law on the National Assembly’s Oversight No. 09/NA, 22 October, 2004 provide explanation on how National Assembly oversees resolution on complaint relevant to settlement.

Law on Settlement of Complaints No 07/NA, 9 November, 2005 define different types of complaint.

Law on Resolving Complaints, No. 53/NA, 15 December 2014 explains different conflict resolution approaches by different governmental bodies at different levels.

Law on Lao Front for National Construction, No. 01/NA, 8 July 2009 define that the Lao Front for National Construction’s roles include collecting and transferring claims or complaints of people regardless ethnic groups, religions, classes, sexes and ages to relevant organization for solutions.

Law on Business Competition No. 60/NA, 14 July 2015 allow conflict resolution through mediation, negotiation and consultation between the conflict parties with participation of third party for evidence.

Law on Local Administrations, No. 68/NA, 14 December 2015 says that village has responsibility to solve compliant and conflicts between villagers as well as building awareness for them on relevant issues.

The government of Lao PDR is currently working on the sixth draft of the Law on Resettlement and Permanent Jobs.

DECREES

Decree on Compensation and Resettlement Management in Development Projects, No. 101/Gov., 05 April 2016 deals with issues related to incompliant with the plan for compensation, resettlement and rehabilitation of people affected by resettlement projects.

Implementation Decree of the Land Law, No. 101/PM, 20 April, 2005 support enforcement of Land Law in the case conflicts occur due to resettlement.

Prime Minister’s Decree on the Organization and Role of the State Inspection Office No.195/PM, 21 March, 2006 outlines functions including study of land disputes and resolution for land administrative sectors.

DIRECTIONS

Ministerial Direction on Systematic Adjudication of Land Use Rights, No 997/MoF, 24 June, 1998 outlines process of land conflict mediation at local level including village level.

Directive of the Minister of Justice on the Spirit, Standards and Steps to Create Conflict-Free Villages No.01/MoJ, 19 March, 2007 gives guidance on conflict establishment free-village.

DECISIONS

Decision on the Organization and Role of the Provincial Land Management Authority No. 62/NLMA, 5 January, 2007.

Decision of the General Secretary of the People’s Revolutionary Party on the Organization and the Role of the Central Inspection Committee, No. 98/P.CC, 15 August, 2006

Decision on the Organization and Role of the Department of Policy and Land Use Inspection No. 20/NLMA, 18 January, 2007.

Decision on the Organization and Role of the District Land Management Authority No. 63/NLMA, 5 January, 2007.

Decision of the Minister of Justice on the Organization and the Role of the Village Mediation Unit No. 02/MoJ, 19 March, 2007

Ministerial Instruction on Adjudications Pertaining to Land Use and Occupation for Land Registration and Titling No.564/NLMA, 6 August, 2007. GUIDELINES Guidelines on Consultation with Ethnic Groups Affected by Public and Private Development Projects. Lao Front for National Construction (LFNC), Vientiane, Lao PDR, 2013.

## Annex 3   Details of the 7 steps of the LLL Grievance Resolution

| Step | Name | Responsibility | Details |
| --- | --- | --- | --- |
| Step1 | Receive and register grievance (National Steering Committee) | Village level: VMC District level: focal point (DAFO-) Provincial level: PSC Central level: NSC | The LLL Project should enable grievants to communicate their grievances to the organization through a variety of channels (e.g. phone, letter, email, Web site, meeting, etc.). Designated staff in the focal point in charge of receiving grievances should: review all claims they receive; consider whether they should handle grievances or refer them onto another more appropriate expert body; undertake the review and respond to the complainant within a timely and efficient manner; provide advice and guidance for the complainant; and ensure access to justice. Establish a centralized database supported by the National Steering Committee and to require that all grievances received be logged into that database using a common protocol and means of recording grievances received. Centralized logging and tracking is important both for accountability and for enabling continuous learning Many grievances may be resolved ‘on the spot’ and informally by LLL project staff, there are still opportunities to encourage these informal resolutions to be logged into a GRM database to: 1) encourage responsiveness; and 2) ensure that repeated or low-level grievances are being noted in the system. |
| Step 2 | Acknowledge, Assess, Assign | Village lev el: VMC District level: focal point (DAFO-DONRE) Provincial level: PSC Central level: NSC | 2.1 Acknowledging receipt: The focal point which has received the grievance should provide a timely communication back to the complainant(s) that their grievance has been received, will be logged and reviewed for eligibility, and if eligible, will generate an initial organizational response. Normally, initial acknowledgement should come within 3-5 days of receipt, and can be in the form of a standard letter or email, with a clearly identified point of contact in the organization, a brief description of the process that will be followed, and a reference name or number for the grievance. Acknowledge receipt and logging of the grievance, and inform the complainant of the procedure for assessing eligibility and generating an initial response. |
|  |  |  | 2.2 Assessing eligibility for the GRM This procedural step should ensure that the issue being raised is relevant to the LLL Project. A decision on eligibility is only meant to trigger an initial organizational assessment and response. It is not an admission that the organization has caused an impact, or a commitment to provide the complainant with any specific form of redress. The staff responsible for the initial response need to follow clear guidelines on what kinds of issues are eligible to be handled through the organization’s GRM, what issues should be referred to other mechanisms and what issues or contexts may not be eligible for an organizational response Those assessing eligibility also need to decide whether the grievance actually should be directed to a different office within the organization, or to a different organization altogether Eligibility often determined on the basis of 4 broad criteria: Does the grievance indicate that the LLL Project or sub-project has caused a negative economic, social or environmental impact on the complainant, or has the potential to cause such an impact? Does the grievance specify what kind of impact has occurred or may occur, and how the program has caused or may cause that impact? Does the grievance indicate that those filing the grievance are the ones who have been impacted, or are at risk of being impacted; or that those filing the grievance are representing the impacted or potentially impacted stakeholders at their request? Does the grievance provide enough information for GRM staff to make a determination on the first three questions? |
|  |  | Village level: VMC District level: focal point (DAFO-DONRE) Provincial level: PSC Central level: NSC | 2.3 Assigning organizational responsibility Grievances should be referred to the most appropriate institution or individual. This referral process will likely depend on the type of issue raised and whether it is low or high risk. |
| Step 3 | Propose a response | Village level: VMC District level: focal point (DAFO-DONRE) Provincial level: PSC Central level: NSC | There are 4 possible types of response: Direct response or action; Stakeholders assessment or engagement Refer to judicial, administrative or national assembly Determine ineligible |
| Step 4 | Develop a proposed response | Village level: VMC District level: focal point (DAFO-DONRE) Provincial level: PSC Central level: NSC | The grievance categorized as relevant will be sent to the Provincial or National Steering Committee for guidance. GRMs typically generate three primary types of response to grievances: Direct action to resolve the grievance Further assessment and engagement with the complainant and other stakeholders to determine jointly the best way to resolve the grievance Determination that the grievance is not eligible for the GRM, either because it does not meet the basic eligibility criteria, or because another mechanism (within the organization or outside it) is the appropriate place for the grievance to go. |
|  |  |  | If the complainant challenges a finding of ineligibility, rejects a proposed direct action, or does not want to participate in a more extensive process of stakeholder assessment and engagement, the National Steering Committee need to clarify the reasons why the complainant does not accept the proposed response, provide additional information, and, where possible, revise the proposed approach. If there is still not agreement, GRM staff need to make sure the complainant understands what other recourse may be available, whether through the judicial system or other administrative channels. For sensitive and challenging cases, the GRM may seek agreement to use independent assessment and mediation or adjudication to seek appropriate resolution of the case. If independent mediation is used, it may be appropriate to set up joint oversight of the mediation process by senior representatives of key stakeholders (e.g. government, international partners, communities, NGOs, and/or businesses involved), to ensure the mediator’s impartiality and to provide strategic oversight of the process. |
| Step 5 | Implement the response to resolve the grievance | Village level: VMC District level: focal point (DAFO-DONRE) Provincial level: PSC Central level: NSC | When there is agreement between a complainant and the GRM to move forward with the proposed action or stakeholder process, then the response should be implemented. In the cases where the initial response is to initiate broader stakeholder assessment and engagement, the assessment process may be conducted by REDD+ Office staff themselves, or others perceived as impartial and effective by the organization, the complainant and other stakeholders. The main purpose of the assessment and engagement process is to clarify: The issues and events that have led to the grievance The stakeholders involved in those issues and events The stakeholders’ views, interests and concerns on the relevant issues Whether key stakeholders are willing and able to engage in a joint, collaborative process (which may include joint fact finding, dialogue and/or negotiation) to resolve the issues How the stakeholders will be represented, and what their decision-making authority will be What work plan and time frame the stakeholders could use to work the stakeholder assessment will produce clarity and agreement among the key stakeholders on a collaborative approach to resolving the issues raised in the grievance; or that one or more key stakeholders are unable or unwilling to participate Whether or not a collaborative process appears viable, the GRM staff needs to communicate the assessment findings to the complainant and other stakeholders, with a recommendation on whether and how to proceed. If a collaborative approach is possible, then REDD+ Office staff is usually responsible for overseeing it. If the engagement process produces agreement on actions to resolve the grievance, then the GRM staff is responsible for overseeing implementation of those actions. In a multi-stakeholder context, several actors may be involved in the solution. |
| Step 6 | Review the response if unsuccessful | Village level: VMC District level: focal point (DAFO-DONRE) Provincial level: PSC Central level: NSC | In some cases, it may not be possible to reach agreement with the complainant on the organization’s proposed response. In a multi-stakeholder dispute, an assessment process may lead to the conclusion that a collaborative approach is not feasible. the GRM staff should review the situation with the complainant, and see whether any modification of the response might meet the concerns of the complainant, the organization, and other stakeholders (see step 4 above) If not, the GRM staff should inform the complainant about other alternatives that may be available, including the use of judicial or other administrative mechanisms for recourse. Whatever alternative the complainant chooses, is important for GRM staff to document their discussion with the complainant and the complainant’s informed choice among alternatives |
| Step 7 | Close out or refer the grievance | Village level: VMC District level: focal point (DAFO-DONRE) Provincial level: PSC Central level: NSC | The final step is to close out the grievance The GRM staff should document the resolution. It may be appropriate to include written documentation; it may be useful to document key lessons learned as well. If the grievance has not been resolved, GRM staff should document steps taken, communication with the complainant and the decisions made by the organization and the complainant about referral or recourse to other alternatives, including legal alternatives GRM documentation on particular cases should maintain confidentiality about details, while making public aggregate statistics on the number and type of grievances received, actions taken and outcomes reached Accurate case documentation using an electronic database is essential for public accountability, organizational learning, and resource planning. |

## Annex 4: Provisional budget for the SEP

| Project stage/ component | Project activities | List of information to be disclosed | Methods proposed | Target stakeholders | Percentage reached | Estimated Budget ($) | Description | Unit (village/ time/ landscapes) | Unit | Unit cost | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Inception |  | ESCP, SEP, CEF, ESMF | Website | Government agencies, CSOs, INGOs, Development partners, communities, private sector | 100% relevant agencies | 50 | Publish on the website | 1 | 1 | 50 | 50 |
| Project Implementation |  | Updated project’s ESF instruments, | Information leaflets, posters and brochures; audio-visual materials, social media and other direct communication channels such as mobile/ telephone calls, SMS, etc; | All stakeholders | 100% stakeholders reached | 5,000 | Information leaflets, posters and brochures; audio-visual materials, social media and other direct communication channels such as mobile/ telephone calls, SMS, etc; |  |  |  | 5,000 |
|  |  | Feedback of project consultations | Public notices; Electronic publications and press releases on the MAF websites; Press releases in the local media (both print and electronic); | All stakeholders | 100% stakeholders reached | 300 | Feedback of project consultations (2 times) post new on the website and new release in newspaper and online News | 10 | 1 | 30 | 300 |
|  |  |  | Process in ethnic languages | Ethnic groups | 100% ethnic representatives reached | 15,000 | Ethnic interpreters | 250 | 2 | 30 | 15,000 |
|  |  | Grievance Redress Mechanisms | Information leaflets, posters and brochures; audio-visual materials, social media and other direct communication channels such as mobile/ telephone calls, SMS, etc; | All stakeholders | 100% communities reached 50% are women | 5,000 | Grievance Redress Mechanisms (comment box) | 250 | 1 | 20 | 5,000 |
| PSFM | 1.2. Participatory Sustainable Forest Management and Restoration in Production and Protection Forests | Project information Forest Management Plan | Information leaflets | Project affected parties | 100% parties reached 50% are women | 6,250 | Information leaflets | 250 | 50 | 1 | 6,250 |
|  |  |  | Posters | Communities | 100% communities reached 50% are women | 875 | Posters | 250 | 1 | 4 | 875 |
|  |  |  | Other IEC materials | Ethnic groups | 60% households in each community | 1,250 | IEC materials | 250 | 1 | 5 | 1,250 |
|  |  |  | Process in ethnic languages | Ethnic groups | 100% ethnic representatives reached | 15,000 | Process in ethnic languages | 250 | 2 | 30 | 15,000 |
| VLD | 2.1. Village Livelihood Development Grants (Agroforestry, NWFPs, etc) 2.2. Vocational Training (forestry, tourism, non-farm) | Project information Community Action Plan | Information leaflets | Project affeted parties | 100% communities reached 50% are women | 6,250 | Information leaflets | 250 | 50 | 1 | 6,250 |
|  |  |  | Posters | Communities | 60% households in each community | 875 | Posters | 250 | 1 | 4 | 875 |
|  |  |  | IEC materials | Communities | 50% participants are women | 1,250 | IEC materials | 250 | 1 | 5 | 1,250 |
|  |  |  | Process in ethnic languages | Ethnic groups | 100% ethnic representatives reached | 15,000 | Process in ethnic languages | 250 | 2 | 30 | 15,000 |
| Nature Based Tourism | 1.1. National Parks, Protected Areas, and Nature-based Tourism 2.3. Nature-based Tourism Support Facility | Project information NBT plan | Information leaflets | Project affeted parties | 100% communities reached 50% are women | 6,250 | Information leaflets | 250 | 50 | 1 | 6,250 |
|  |  |  | Posters | Communities | 60% households in each community | 875 | Posters | 250 | 1 | 4 | 875 |
|  |  |  | IEC materials | Communities | 50% participants are women | 1,250 | IEC materials | 250 | 1 | 5 | 1,250 |
|  |  |  | Process in ethnic languages | Ethnic groups | 100% ethnic representatives reached | 15,000 | Process in ethnic languages | 250 | 2 | 30 | 15,000 |
| Project Close Out |  | Enf of project report/information | Information stands | All stakeholders | 100% stakeholders reached | 1,250 | Government | 5 | 1 | 250 | 1,250 |
|  |  | Estimated overall total |  |  | 96,725 |  |  |  |  |  |

The Asia-Pacific Workshop on Women’s Inclusion for Sustainable Forests and Climate: What Works? USAID-funded Lowering Emissions in Asia’s Forest (LEAF) in collaboration with the UN-REDD Programme (UN-REDD) and Women Organizing for Change in Agriculture and Natural Resource Management (WOCAN).

Gender in REDD+: A handbook for grassroots facilitators. Questions and Answers. Copyright © RECOFTC, November 2013, Bangkok, Thailand

Guidelines on Stakeholder Engagement in REDD+ Readiness, With a Focus on the Participation of Indigenous Peoples and Other Forest-Dependent Communities. April 20, 2012 (revision of March 25th version).

Joint Forest Carbon Partnership Facility /UN-REDD Programme Guidance Note for REDD+ Countries: Establishing and Strengthening Grievance Redress Mechanisms, June 2015.

2014 Guidance Note for Environmental Impact Assessment Approvals for Agriculture and Forestry Plantations. Government of Lao PDR, Ministry of Natural Resources and Environment, Department of Environmental and Social Impact Assessment. If the “traditional and customary” approach in resolving the dispute fails the concerned parties should be able to use an Alternative Dispute Resolution process which should be documented under the project’s Management Plan. This involves an escalating resolution process, incorporating negotiation, mediation, or arbitration before initiating any litigation process.

Customary Law and Practices in Lao PDR. Ministry of Justice, Law Research and international Cooperation Institute. United Nation Development Program, Democratic Governance Thematic Fund. Vientiane, Lao PDR. http://issat.dcaf.ch/esl/Home/Community-of-Practice/Resource-Library/Authors/Steeve-Daviau

http://223.27.200.4/www.undp.org/content/dam/laopdr/docs/Reports%20and%20publications/Customary_Law_Laos2011_english_master1.pdf

For details see: Final Evaluation for the Legal Awareness and Conflict Transformation Project in Lao PDR, Mennonite Central Committee (MCC) Laos, 2017; Final Evaluation the Strengthening the right of women and encourage their participation in civil society Project, Association for the Development of Women and Legal Education (ADWLE) - Bread for the World – Protestant Development Service.

Daviau, S. (2010) People’s Perspective on Access to Justice Survey in Lao PDR, An Assessment in Four Provinces of Lao PDR. Ministry of Justice, Lao Bar Association, supported by the United Nations Development Project, Vientiane, Lao PDR.